## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2024 | Czechia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-1 CZ 0-001 | MF 2021-2 CZ 0-003 | Scheme (Part A): Support for photovoltaic power plants with installed capacity up to 1 MW of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Any body based in the Czech Republic and holding a business licence in the energy sector pursuant to Act no. 458/2000 Coll (for more details and exceptions see Annex A). The scheme supports legal entities, municipalities, individuals as well as communities for renewable energy. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 663770000 | 548570000 | 192000000 | 192000000 | 134700483.528 | 0 | 0 | NR | 1306 | 4522000 | 508.3 | 3888000 | 0.521 | 452 | 0 | 49.3827 | Yes, 2020, 2021 | 1 call for this programme continued in 2023, with a total of 458 projects were delivered in this call in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
2 | MF 2021-1 CZ 0-002 | MF 2022-1 CZ 0-008 | Scheme (Part B): Support for photovoltaic power plants with installed capacity above 1 MW of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Any body based in the Czech Republic and holding a business licence in the energy sector pursuant to Act no. 458/2000 Coll. Significant number of projects is expected from electricity generators according to Art. 10c of the Emission Trading Directive, then legal entities outside the EU ETS sector, municipalities, individuals as well as communities for renewable energy. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 3803000000 | 3143000000 | 1100000000 | 1100000000 | 309267183.0924 | 0 | 0 | NR | 0 | 29588000 | 0 | 25445000 | 0 | 2959 | 0 | 43.2305 | Yes, 2020, 2021 | No call was launched in 2023, but 47 projects from previous calls had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
3 | MF 2021-2 CZ 0-001 | NR | Scheme (Part A): Modernisation of energy sources priority investments of the Programme “HEAT” | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | C-Energy Planá s.r.o., Veolia Energie ČR, a.s., Veolia Energie Kolín, a.s., Teplárna České Budějovice, a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 657608696 | 543478261 | 250000000 | 250000000 | 64672742.3575 | 29590842.79 | 0 | NR | 0 | 14438000 | 0 | 19738000 | 0 | 945 | 1.4992 | 12.6659 | Yes, 2020 | 2 projects from previous calls had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
4 | MF 2021-2 CZ 0-002 | NR | Scheme (Part A1): Modernisation of energy production priority investments of the Programme ENERG ETS | Priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 223586957 | 184782609 | 85000000 | 85000000 | 30000000 | 0 | 0 | NR | 0 | 7937000 | 0 | 10124000 | 0 | 315 | 0 | 8.3959 | Yes, 2020 | NR | NR | NR | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
5 | MF 2022-1 CZ 0-001 | MF 2023-2 CZ 0-010 | Scheme: Modernization of energy sources to natural gas with CHP; priority investment of the Programme “HEAT” (Modernization of thermal energy supply systems) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Veolia Energie ČR, a.s., C-Energy Planá s.r.o., Teplárna Písek, a.s., ČEZ Teplárenská, a.s., CTZ s.r.o., Veolia Průmyslové služby ČR, a.s., | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 499125000 | 412500000 | 198000000 | 198000000 | 60273943.5996 | 26556154.92 | 0 | NR | 0 | 17222000 | 0 | 11460000 | 0 | 0 | 2.3173 | 17.2775 | Yes, 2020, 2021 | No call was launched in 2023, but 8 projects from previous calls had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
6 | MF 2022-1 CZ 0-002 | NR | Scheme: Modernisation of energy sources to natural gas with CHP; priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | BONATRANS GROUP a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 191583333 | 158333333 | 76000000 | 76000000 | 2219087.8301 | 0 | 0 | NR | 0 | 10556000 | 0 | 6550000 | 0 | 0 | 0 | 11.6031 | Yes, 2020, 2021 | No call was launched in 2023, but 1 project from previous call had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
7 | MF 2022-1 CZ 0-003 | NR | Scheme: Modernisation of energy sources to natural gas with CHP; priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) (P‐5 Modernization of natural gas energy sources with CHP) | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 95791667 | 79166667 | 38000000 | 38000000 | 0 | 0 | 0 | NR | 0 | 4722000 | 0 | 960000 | 0 | 0 | 0 | 39.5833 | Yes, 2020, 2021 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
8 | MF 2022-1 CZ 0-004 | NR | Scheme: Municipal PV - small municipalities; priority investment of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Czech small municipalities with less than 3,000 inhabitants. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 161333333 | 133333333 | 100000000 | 100000000 | 55095287.2781 | 0 | 0 | NR | 0 | 1055000 | 0 | 909000 | 0 | 105.7 | 0 | 110.011 | Yes, 2021 | 1 call for this programme continued in 2023, with a total of 1109 projects were delivered in this call in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
9 | MF 2022-1 CZ 0-005 | NR | Scheme: Municipal PV – communal renewable energy; priority investment of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Czech municipalities and the entities entirely in public/municipal ownership. | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 484000000 | 400000000 | 200000000 | 200000000 | 11597779.8584 | 0 | 0 | NR | 0 | 3166000 | 0 | 2727000 | 0 | 317 | 0 | 73.3407 | Yes, 2021 | 1 call for this programme continued in 2023, with a total of 149 projects were delivered in this call in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
10 | MF 2022-1 CZ 0-006 | NR | Scheme: Modernisation of public lighting; priority investment of the Programme “LIGHTPUB” (Modernization of public lighting systems) | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Regions, municipalities, voluntary associations of municipalities, city districts of the capital city of Prague and companies owned by a public entity or operators of public lighting systems. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 53777778 | 44444444 | 40000000 | 40000000 | 0 | 0 | 0 | NR | 0 | 85000 | 0 | 74000 | 0 | 0 | 0 | 540.5405 | Yes, 2021 | NR | NR | There is a delay in starting the scheme due to effort to evit overlapping with other support programs at the national level. However, the first call for project proposals is to be launched in Q2/2024. | NR | The programme document of the LIGHTPUB programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
11 | MF 2022-1 CZ 1-001 | NR | Scheme (Part 1A): Modernization of energy sources to biomass without CHP; non-priority investments of the Programme “HEAT” (Modernization of thermal energy supply systems) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Teplárna Otrokovice a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 623711340 | 515463918 | 250000000 | 250000000 | 5024625.621 | 0 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 2222000 | 0 | 14000000 | 0 | 1240 | 0 | 17.8571 | Yes, 2020, 2021 | No new call was announced in 2023, but a call announced in 2022 was ongoing. In 2023, 4 projects applied for this call, 1 of which has already received a decision from the Minister. | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
12 | MF 2022-1 CZ 1-003 | NR | Scheme (Part 1C): Modernization of energy sources to natural gas without CHP; non-priority investments of the Programme “HEAT” (Modernization of thermal energy supply systems) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | ČEZ, a. s., Veolia Energie ČR, a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 330000000 | 272727273 | 120000000 | 120000000 | 6738237.5976 | 1720737.5369 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 10556000 | 0 | 15510000 | 0 | 0 | 0.11094 | 7.7369 | Yes, 2020, 2021 | No new call has been launched in 2023, but 1 project from previous call had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
13 | MF 2022-1 CZ 1-004 | NR | Scheme (Part 2A): Modernisation of energy sources to biomass without CHP; non-priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Non-priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 82329897 | 68041237 | 33000000 | 33000000 | 0 | 0 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 277000 | 0 | 2540000 | 0 | 160 | 0 | 12.9921 | Yes, 2020, 2021 | NR | NR | NR | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
14 | MF 2022-1 CZ 1-006 | NR | Scheme (Part 2C): Modernisation of energy sources to natural gas without CHP; non-priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Non-priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Moravskoslezské cukrovary s.r.o. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 244750000 | 202272727 | 89000000 | 89000000 | 3333986.3903 | 0 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 6944000 | 0 | 10340000 | 0 | 0 | 0 | 8.6074 | Yes, 2020, 2021 | No new call was announced in 2023, but a call announced in 2022 was ongoing. 1 project has already received a decision from the Minister in 2023. | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
15 | MF 2022-1 CZ 1-008 | NR | P-2E: Scheme – Modernization of natural gas energy sources without CHP, ENERG ETS (CZ) Programme | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Slévárny Třinec, a.s., Cukrovar Vrbátky a.s., Tereos TTD, a.s., ORLEN Unipetrol RPA s.r.o., PAPOS Trade s.r.o. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 49500000 | 40909091 | 18000000 | 18000000 | 10667622.4623 | 0 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 1389000 | 0 | 260000 | 0 | 0 | 0 | 69.2308 | Yes, 2020, 2021 | 3 projects from previous call had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
16 | MF 2022-2 CZ 0-001 | MF 2023-2 CZ 0-009 | Energy Efficiency and Energy Savings in houses and buildings for Residential Sector (HouseEnerg Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Owners of single-family residential houses (as defined by the Act No.283/2021 Coll. Building Act. and owners of the apartment buildings as defined by the Act No. 501/2006. Single-family residential houses and apartment buildings will be used for non-commercial activity. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2904000000 | 2400000000 | 1200000000 | 1200000000 | 443061928.5339 | 443061928.5339 | 0 | NR |  | 16790000 | 311766 | 8003000 | 0 | 703 | 55.362 | 149.9438 | No | In 2023 the scheme was re-approved S2/2023. | NR | No | NR | The programme document of the HOUSEnerg programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
17 | MF 2022-2 CZ 0-002 | NR | Improving energy efficiency in industrial production under the EU ETS | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | TŘINECKÉ ŽELEZÁRNY, a. s., Slévárny Třinec, a.s., LASSELSBERGER, s.r.o., Tereos TTD, a.s., Holcim (Česko), a.s., Synthomer a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 1815000000 | 1500000000 | 700000000 | 700000000 | 40646156.275 | 0 | 0 | NR | 0 | 54167000 | 0 | 7089000 | 0 | 0 | 0 | 98.7445 | Yes, 2020, 2021 | 2 new projects from previous call had a contract signed between the beneficiary and the SEF in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
18 | MF 2022-2 CZ 0-003 | NR | Financial instrument for improving energy efficiency in business (ENERG Programme) | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Business entities except for the entities covered by the EU ETS system. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 403333333 | 333333333 | 100000000 | 100000000 | 0 | 0 | 0 | NR | 0 | 441000 | 0 | 250000 | 0 | 0 | 0 | 400 | Yes, 2021 | NR | NR | There is a delay in starting the scheme due to prolonged negotiations with the bank implementing the scheme on the subject matter of setting the conditions properly in the calls in accordance with the scheme. In 2024, the scheme is planned to start by launching its first call for project proposals. | NR | The programme document of the ENERG programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
19 | MF 2022-2 CZ 1-001 | NR | Renewable Modernisation of Energy Sources for Residential Sector (HOUSEnerg Programme) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Owners of single-family residential houses (as defined by the Act No.283/2021 Coll. Building Act. and owners of the apartment buildings as defined by the Act No. 501/2006. Single-family residential houses and apartment buildings will be used for non-commercial activity. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2420000000 | 2000000000 | 1000000000 | 1000000000 | 26474433.3266 | 26474433.3266 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 339444 | 83130000 | 95351 | 36199000 | 0 | 2681 | 0.73136 | 27.6251 | No | 60521 projects have already received a decision from the Minister in 2023. | NR | No | NR | The programme document of the HOUSEnerg programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
20 | MF 2023-1 CZ 0-001 | NR | Modernization of the ŠKO-ENERGO heating plant | Priority | Project | Tender ongoing | NR | ŠKO-ENERGO, s.r.o. | CZ02 Střední Čechy | 184299843 | 152313919 | 89376476 | 89376476 | 89376476 | 0 | 0 | NR | 0 | 971366 | 0 | 364803 | 0 | 190 | 0 | 244.9993 | Yes, 2022 | NR | 2028-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
21 | MF 2023-1 CZ 0-002 | NR | Modernization of “Brno-North” Heat Source for Brno City Heat Energy Supply System | Priority | Project | Construction ongoing | NR | Teplárny Brno, a.s. | CZ06 Jihovýchod | 147393780 | 121813042 | 79568908 | 79568908 | 79568908 | 4726071.2922 | 0 | NR | 0 | 169946 | 0 | 37777 | 0 | 43 | 125.1045 | 2106.2792 | Yes, 2021, 2022 | NR | 2025-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
22 | MF 2023-1 CZ 0-003 | NR | Modernization of WtE plant of the SAKO Brno to increase processing capacity and operational efficiency | Priority | Project | Construction ongoing | NR | SAKO Brno, a.s. | CZ06 Jihovýchod | 281936597 | 233005452 | 116780718 | 116780718 | 116780718 | 0 | 0 | NR | 0 | 137124 | 0 | 61008 | 0 | 0 | 0 | 1914.187 | Yes, 2021, 2022 | NR | 2026-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
23 | MF 2023-1 CZ 0-004 | NR | Construction of WtE facility in the Mělník power plant location | Priority | Project | Tender ongoing | NR | ČEZ, a. s. | CZ02 Střední Čechy | 656427605 | 542502153 | 249946208 | 249946208 | 249946208 | 0 | 0 | NR | 0 | 134439 | 0 | 46708.11 | 0 | 0 | 0 | 5351.2379 | Yes, 2021, 2022 | NR | 2027-07-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
24 | MF 2023-1 CZ 0-005 | NR | Scheme: Energy efficiency and savings in modernisation and development of pipelines in the district heating and cooling (DHC) - priority investment of the Programme “HEAT” (Modernization of thermal energy supply systems) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Pražská teplárenská a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 423500000 | 350000000 | 350000000 | 350000000 | 1649848.3316 | 0 | 0 | NR | 0 | 1638889 | 0 | 674300 | 0 | 0 | 0 | 519.0568 | Yes, 2020, 2021, 2022 | In 2023, 1 call was launched and 2 projects came in, 1 of which has already received a decision from the Minister in 2023 | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
25 | MF 2023-1 CZ 0-007 | NR | Replacement of a coal block with a gas source (STAGE I) - Opatovice | Priority | Project | Tender ongoing | NR | Elektrárny Opatovice a.s. | CZ05 Severovýchod | 128069377.81 | 105842461 | 64255276 | 64255276 | 64255276 | 0 | 0 | NR | 0 | 177688 | 0 | 136064 | 0 | 0 | 0 | 472.243 | Yes, 2022 | NR | 2026-05-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
26 | MF 2023-1 CZ 0-008 | NR | Waste to energy plant in Písek | Priority | Project | Tender ongoing | NR | ZEVO PÍSEK s.r.o. | CZ03 Jihozápad | 105987258 | 87592775 | 53864049 | 53864049 | 53864049 | 0 | 0 | NR | 0 | 39283 | 0 | 14725 | 0 | 0 | 0 | 3657.9999 | No | NR | 2028-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
27 | MF 2023-1 CZ 0-009 | NR | The Construction of a steam-gas cycle PPC1 at The UE Komořany | Priority | Project | Tender ongoing | NR | United Energy, a.s. | CZ04 Severozápad | 117208653 | 96866655 | 57784105 | 57784105 | 57784105 | 0 | 0 | NR | 0 | 267100 | 0 | 149991 | 0 | 0 | 0 | 385.2505 | Yes, 2022 | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
28 | MF 2023-1 CZ 0-010 | NR | Waste-to-Energy Facility EVO – Komořany, Most | Priority | Project | Tender ongoing | NR | United Energy, a.s. | CZ04 Severozápad | 249869718 | 206503899 | 105586266 | 105586266 | 105586266 | 0 | 0 | NR | 0 | 145986 | 0 | 53349 | 0 | 0 | 0 | 1979.1611 | Yes, 2022 | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
29 | MF 2023-1 CZ 0-011 | NR | Energy efficiency and energy savings in public buildings (ENERGov Programme) | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Public and state entities and their organizations, such as schools, cultural and sports facilities, universities, public research institutions, business companies owned 100% by a public entity, state enterprises, organizational units of the state, state funded organizations, associations, churches, foundations, etc. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 726000000 | 600000000 | 300000000 | 300000000 | 0 | 0 | 0 | NR | 0 | 76036 | 0 | 24700 | 0 | 0 | 0 | 12145.749 | Yes, 2021, 2022 | 2 calls were launched, both ongoing, with 4 recieved projects | NR | No | NR | The programme document of the ENERGov programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
30 | MF 2023-1 CZ 0-013 | NR | Energy efficiency and energy savings in new buildings for public sector (ENERGov Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | LOŠBATES, dobrovolný svazek obcí (voluntary association of municipalities); Střední pedagogická škola Boskovice, příspěvková organizace (Secondary Pedagogical School Boskovice, contributory organization) | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 468750000 | 375000000 | 150000000 | 150000000 | 10373866.8461 | 0 | 0 | NR | 0 | 57700 | 0 | 44528 | 0 | 0 | 0 | 3368.6669 | No | 1 call was launched, recieved 65 projects, 3 with a decision from the Minister in 2023 | NR | No | NR | The programme document of the ENERGov programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
31 | MF 2023-2 CZ 0-002 | NR | Construction of OV VP4 media preheating | Priority | Project | Construction ongoing | NR | Třinecké železárny, a. s. | CZ08 Moravskoslezsko | 13592496.63 | 11233468.29 | 4648807.34 | 4648807.34 | 4648807.34 | 0 | 0 | NR | 0 | 17360 | 0 | 14077.179 | 0 | 0 | 0 | 330.2371 | No | NR | 2025-04-01 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
32 | MF 2023-2 CZ 0-003 | NR | EGT-transition to low-emission heat and power generation – Stage 1. | Priority | Project | Tender ongoing | NR | Energotrans, a. s. | CZ02 Střední Čechy | 611085139 | 505029040 | 307762161 | 307762161 | 307762161 | 0 | 0 | NR | 0 | 921644 | 0 | 568423 | 0 | 0 | 0 | 541.4316 | Yes, 2022 | NR | 2028-12-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
33 | MF 2023-2 CZ 0-005 | NR | The Construction of a steam-gas cycle PPC2 at The UE Komořany | Priority | Project | Not started | NR | United Energy, a.s. | CZ04 Severozápad | NA | 103064365 | 62399645 | 62399645 | 62399645 | 0 | 0 | NR | 0 | 267100 | 0 | 149991 | 0 | 0 | 0 | 416.0226 | No | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
34 | MF 2023-2 CZ 0-006 | NR | Replacement of a coal block with a gas source - STAGE II | Priority | Project | Tender ongoing | NR | Elektrárny Opatovice a.s. | CZ05 Severovýchod | 94489667 | 78090634 | 47848099 | 47848099 | 47848099 | 0 | 0 | NR | 0 | 176606 | 0 | 135131.8 | 0 | 0 | 0 | 354.0847 | No | NR | 2027-04-05 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
35 | MF 2023-2 CZ 0-008 | NR | EVO Planá - Energie z odpadu Táborska / WtE Planá | Priority | Project | Not started | NR | C-Energy Planá s.r.o. | CZ03 Jihozápad | 108565145 | 89723261 | 58441401 | 58441401 | 58441401 | 0 | 0 | NR | 0 | 145016 | 0 | 57400 | 0 | 0 | 0 | 1018.1429 | Yes, 2022 | NR | 2027-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
Note on O3: RM od r. 2021 do konce 2023
Note on O6: kurz k 18.4.2024
Note on S6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W6: 7221100003 - FVE Impregnace Soběslav
Note on Y6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S40: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U40: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W40: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y40: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.

## Overview Planned Investment
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment/Název a reference investice | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) / | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investmen
1 | Individual investment: Greening of the Chomutov Heating Plant - 2nd stage - ACTHERM, spol. s r.o. | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 113102635 | New Wte/ZEVO construction. Replacement(Et Chomutov) of the existing dry bottom lignite boilers of K1 (output 49.7 MWt and TG1 turbine with electrical power of 20 MWe) and K3 (output 34.4 MWt and TG2 turbine with electrical power of 6 MWe) with a water-tube steam boiler with a predicted thermal output of 19.5 MWt and electrical power of 6.35 MWe. The estimated minimum guaranteed availability (load) is 8,000 hours/year | pending | 67428516 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform. It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
2 | Individual investment: Renewal of the heat and power plant Energetika - Plzeňská Teplárenská, a.s. | State Environmental Fund of the Czech Republic | CZ03 Jihozápad | 157270201 | The investment aims to replace lignite with natural gas which will be used as fuel for the Combine cycle heat and power plant. This includes mainly the installation of a new gas turbine machine hall, gas booster compressor, a heat recovery steam generator with steam reheating and a new steam turbine machine hall with accessori. The maximum thermal output of the CCGT would be 83 MWth and the maximum electrical output would be 87,7 MWel ( Nominal electric power output of the source 1 is 60 MWe and source 2 is 40MWe). | pending | 76939459 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
3 | Individual investment: Replacement of a coal block with a gas source - STAGE III. - Elektrárny Opatovic, a.s. | State Environmental Fund of the Czech Republic | CZ05 Severovýchod | 105054197.3003 | The main objective of presented project is to replace existing coal-fired source with two new sources installed power by combined cycle gas turbines (CCGT, source 1) and heat recovery steam generators (HRSG, source 2). This project replaces the existing K2 coal-fired boiler, which will be shut down after the implementation of the project and will no longer be operated.Future state: PT3 - Gas Turbine – Source 1 - 59,6MWe P3 – Heat recovery steam generator (HRSG) and TG6 together Source 2 - 56,5MWt and 65 MWe. | pending | 63305519 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
4 | Individual investment: Replacement of a coal block with a gas source - STAGE IV - Elektrárny Opatovice, a.s. | State Environmental Fund of the Czech Republic | CZ05 Severovýchod | 131820831.4914 | The main objective of presented project is to replace existing coal-fired source with two new sources installed power by combined cycle gas turbines (CCGT, source 1) and heat recovery steam generators (HRSG, source 2) PT3 - Gas Turbine – Source 1 - 65,6MWe, P3 – Heat recovery steam generator (HRSG) and TG6 together Source 2 - 75,8MWt and 65 MWe. This project replaces part of the output of the existing K3 coal-fired boiler. | pending | 80878970 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
5 | Individual investment: PPC (including storage) Transition to low-emission heat and power generation, stage 2. Energotrans, a.s. (ČEZ) | State Environmental Fund of the Czech Republic | CZ02 Střední Čechy | 600000000 | The subject of the project is the replacement of the heat source in the thermal energy supply system with a change of the fuel base from coal to natural gas in combination with a high-efficiency CHP. | pending | 180000000 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
6 | Individual investment: PPC (including storage) možná: Transition to low-emission heat and power generation, stage 3. Energotrans, a.s. (ČEZ) | State Environmental Fund of the Czech Republic | CZ02 Střední Čechy | 1000000000 | The subject of the project is the replacement of the heat source in the thermal energy supply system with a change of the fuel base from coal to natural gas in combination with a high-efficiency CHP. | pending | 7500000000 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
7 | Individual investment: Strategy for a green city - ZEVO Vráto | State Environmental Fund of the Czech Republic | CZ03 Jihozápad | 388234232 | The main objective of the project is to install a new Waste-to-Energy (ZEVO) unit with state-of-the-art technology for combusting a mixture of municipal solid waste (MSW). ZEVO Vráto will be operated as a combined source of heat and power. | pending | 189022951 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
8 | Individual investment: ZEVO Opatovice / WtE Opatovice | State Environmental Fund of the Czech Republic | CZ05 Severovýchod | 288021452 | The main goal of the project is the construction of a facility for the energy utilization of municipal waste with a capacity of 150,000 t/year, using waste from close driving distance, i.e. from municipalities and cities mainly from the Královéhradecky and Pardubice regions. Furthermore, there will be a reduction in CO2 production from fossil fuels and the consumption of primary non-renewable energy while maintaining the supply of heat to the local central heating distribution system in combination with the production of electricity. | pending | 153079957 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
9 | Individual investment: UL_PPC 100 MWth (150 Mwe), Trmice | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 316483550 | The aim of the project UL_PPC 100 MWth (150 Mwe), Trmice is the construction of a steam-gas cycle (PPC) in the configuration of two combined cycle gas turbines (CCGT) incl. HRSG and one shared steam turbine with total thermal output to district heating system (DHS) of 100 MWth and electrical output 150 MWe. The new heat source will replace the heat from the existing coal-fired boilers K5, K6 supplied to the DHS as part of the phased renewal of the entire site. | pending | 198606493 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
10 | Individual investment: Renewal of the source - Energetics | State Environmental Fund of the Czech Republic | CZ03 Jihozápad | 154256904 | The goal of the project is the decarbonization of the production block, which consists in the installation of a steam-gas unit. | pending | 75465299.88 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
11 | Individual investment: Heating plant T600 | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 1022262414 | The existing lignite heating plant was put into operation in the 1960s and underwent a major renovation in the 1990s. Due to the poor technical condition of the facility and the need to address the stricter BREF LCP emission limits set by current and expected legislation after 2025, it was decided to shut down the heating plant; replacement with a new natural gas-based cogeneration source must take place by the end of 2027 at the latest. | pending | 481825214 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
12 | Individual investment: New energy source KD7 | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 249281930 | The presented project is focused on achieving energy savings and reducing CO2 emissions. The project addresses the comprehensive modernization of nitric acid production, where the existing two plants will be replaced and a new modern plant will be built instead. The modernization of the plant will also enable the shutdown of a fluidized bed boiler, which burns lignite. The project also includes instalation of a new turbine. The device meets the condition of electricity production through high-efficiency combined heat and power generation. | pending | 80997314 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
13 | Individual investment: Modernization and decarbonization of steel production | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 821078937.1082 | The proposed solution consists in changing the technology of steel production in Třinecké železárny with the aim of significantly reducing the emission footprint of production. The new technology consists in the production of steel in electric arc furnaces mainly from steel scrap, while the recyclability of steel is fully utilized and the main energy input is electrical energy (instead of the current coke and pulverized coal as part of "ore technology"). In addition to scrap, ore input can also be used in the production of steel in electric arc furnaces, namely so-called directly reduced iron, which is produced by reducing ore pellets using natural gas, carbon (or hydrogen). | pending | 429767481.456 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
14 | Individual investment: Modernisation of nitric acid production | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 138500000 | The project is focused on replacing the current nitric acid production plants with a new nitric acid production plant. The installation of a new modern line for the production of nitric acid mainly brings savings in electricity. The reason is that the current technologies use electric engines to drive the turbogenerators. With the new line, the turbogenerator is driven by a steam turbine. The heat required to produce steam is generated in the boiler connected to the reactor during the combustion of ammonia. Excess steam is used to produce electricity or to supply steam to the plant premises. | pending | 60211773 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
15 | Individual investment: ALFAGEN – Modernisation of the melting and casting technology | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 172685616 | The core of the project is mainly the acquisition of new technological equipment and machines, which will consume less natural gas and electricity thanks to modern technologies. The devices will be installed in the newly built hall, which will also be less energy demanding. The project is divided into two parts: 1) Replacement of the melting and direct casting process (ALUM), 2) Replacement of the melting and continuous casting process (ALUF). | pending | 79117830 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
16 | Individual investment: Reduction of CO2 emissions during heat production | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 207984992 | The primary objective of the project is to transition from burning coal to sustainable energy sources, specifically biomass, while ensuring sufficient heat and electricity capacity for a plant and for supplying heat to the nearby town. | pending | 124526841 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
17 | Individual investment: New Polymerization Plant | State Environmental Fund of the Czech Republic | CZ02 Střední Čechy | 269249626 | The project concerns the replacement of outdated polymerization technology with regard to modern procedures and technical, ecological, energy and economic aspects of operation. | pending | 103126483 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
18 | Individual investment: Decarbonisation of the Karviná CHP Plant – part: Multi-fuel Boiler with Combined Heat and Power Generation and Gas-fired CHP Installation with Combined Heat and Power Generation | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 318159945 | The present project addresses the phase-out of firing coal and its replacement by firing refuse-derived fuel (RDF) and biomass in a multi-fuel boiler along with natural gas at other energy installations. The project replaces a coal-fired heat source in a district heating system with a new installation. The project involves the construction of new energy installations, a change of fuels, and an increase in efficiency. | pending | 204589717 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
19 | Individual investment: Modernisation of the Olomouc CHP Plant – Part: Multi-Fuel Boiler and Gas-fired CHP Unit | State Environmental Fund of the Czech Republic | CZ07 Střední Morava | 168397436 | The retrofit of the fluidised bed boiler to pass from firing brown or hard coal to refuse-derived fuel (RDF) and biomass. | pending | 102218068 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
20 | Individual investment: CV_PM 45 MW EPR, Prunéřov | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 116899786 | The subject of the project is the construction of a gas power plant consisting of 4 gas engines while the heat supply from the coal-fired units will be phased out. | pending | 72539137 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
21 | Scheme: Installation of photovoltaic power plants in households (RES+ programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2288000000 | Support is provided for the acquisition and installation of a new photovoltaic system up to 10 kWp connected to indoor electricity distribution system, intended for the production of electricity with priority use of the energy produced in the residential parts of the building, the supply of unused energy to distribution system or its use in the local energy community to which the building belongs is connected to. For sake of grid stability, energy storage technologies can be supported as a part of the project. | pending | 500000000 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this scheme resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
22 | Scheme: Aid for installation of photovoltaic power plants to address self-consumption of energy (in enterprises; RES+ programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 1430000000 | Investment aid for new installed capacity of photovoltaic power plants to address self-consumption of energy in enterprises, as a consequence of addressing the volatility of energy prices and in particular to accelerate the transition to self-consumption of renewable energy. | pending | 500000000 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this scheme resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
23 | Scheme: Modernisation of public transport – electric and H2 passenger trains (TRANSGov programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 813588353 | The aim of the investment is to reduce energy consumption in regional public railway transport by replacement of diesel vehicle units by low-emission rolling stock and modernisation of electricity-driven multiple units. Passenger transport rolling stock with alternative drive (electric power transmission, possibly in combination with battery and hydrogen) for passenger transport is supported. | pending | 615085029 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this scheme resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
24 | Scheme: Modernisation of public transport – buses, trolley buses and tramways (TRANSGov programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 599323029 | The scheme deals with measures leading to the fulfilment of the goals of so-called clean mobility and increasing the share of RES in public transport. It also aims to improve air quality and reduce emissions of CO2 in public transport by modernisation and switch to low-emission vehicles. Electricity-driven and H2 buses, (partial) trolley buses and tramways for public passenger transport would be supported. | pending | 299661515 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this scheme resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee in 2024.
25 | Individual investments: H2 infrastructure projects (GREENGAS programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Support for individual projects concerning H2 infrastructure (Several projects are envisaged in connection with Sovereignty Seal projects with Germany) | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | Yes, pending | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
26 | Individual investments: Individual innovative & sovereignty seals projects: in 2024, the project proposed is "H2@GasNet Distribution Network" (I+ programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Aid for innovative projects receiving support from Innovation Fund in their measures falling into Modernisation Fund | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | Yes, pending | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
27 | Scheme: Electric energy standalone accumulation (RES+ programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Support of standalone accumulation of electric energy produced from PV power plants | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
28 | Scheme: New buildings in higher energy standard (ENERGov programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Aid for construction of new buildings in higher than passive energy standard (active buildings) | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
29 | Scheme: Freight and freight train transport (TRANSCom programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Measures to increase energy efficiency in freight and freight train commercial transport | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
30 | Scheme: Support tool for production/use of H2 (GREENGAS programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Measures to support building of infrastructure for production and use of H2 | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No
31 | Scheme: Electricity grids modernisation and development (ELEGRID programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Modernisation and development of electricity grids (distribution and transmission networks) | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR
32 | Scheme: Energy communities (KOMUNERG programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | planned | Aid for establishment of energy communities | pending | planned | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | NR

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia