## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2023 | Estonia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-2 EE 0-001 | MF 2022-2 EE 0-001, MF 2023-2 EE 0-001 | Programme for improvement of energy efficiency and renewable energy use in public sector buildings | Priority | Scheme | Tender ongoing | https://www.riigiteataja.ee/akt/109082022031 | Central government | Estonia, Harju County; Estonia Tartu County | 68000000 | 68000000 | 68000000 | 68000000 | 20647800 | 4950 | 0 | N/A | 0 | 21330 | 0 | 9765 | 0 | 0 | 0 | 2114.47 | Yes, 2023 | The first Call for Applications based on the referred ministerial regulation, with the call budget of 28 million euros, was published in October 2022 with the deadline for submitting application set on 31st January 2023. Two applications were submitted, both were approved. Based on evaluation results, these applications were granted support in the total amount of 20,6 million euros. The remaining part of the initially planned call budget was added to the planned budget of the next call for applications. The second Call for Applications was published in November of 2023 with the deadline for submitting application set on 31st January 2024. | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Programme for improvement of energy efficiency and renewable energy use in public sector buildings | Priority | Scheme | Tender ongoing | https://www.riigiteataja.ee/akt/128092023021 | Local municipalities |  | 102000000 | 102000000 | 102000000 | 102000000 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Yes, 2023 | The first Call for Applications based on the referred ministerial regulation, with the call budget of 40 million euros and implementation costs 142 000 euros, was published in October 2023 with the deadline for submitting application set on 31st January 2024. Submitted applications are under evaluation. The evaluation results and the list of supported projects will be announced in May 2024. The second call for Applications is planned to open in 2024. | N/A | N/A | N/A | N/A | N/A | N/A
2 | MF 2021-2 EE 0-002 | MF 2022-2 EE 0-002, MF 2023-2 EE 0-002 | Energy-efficient low-emission public transport programme | Priority | Scheme | Construction ongoing | Planning schemes/projects under Modernisation Fund https://www.riigiteataja.ee/akt/122092023001. Legal base for planning energy efficient public transport https://www.riigiteataja.ee/akt/130062023008 with Annex https://www.riigiteataja.ee/aktilisa/1241/1202/3007/VV_104m_lisa.pdf. State budget act https://www.riigiteataja.ee/en/eli/ee/Riigikogu/act/531052024001/consolide which includes Energy Sector Development Plan 2030 and Transport Development Plan 2021-2035. | AS Eesti Liinirongid | Estonia, Tallinn | 90713449 | 90713449 | 90713449 | 90713449 | 90713449 | 13607017 | N/A | N/A | 0 | 300000 MWh | 0 | 270000 | 0 | N/A | 0 | 335.9757 | Yes, 2023 | The procurement procedure for 10 electric trains has been carried out and the contract with the successful tenderer was signed on 19.12.2022. The trains are in production and will be delivered in 2025 but according to the signed contract the final delivery of 10 electric trains will be in March, 2026. | 2026-03-31 | N/A | N/A | N/A | N/A | N/A
|  |  | Energy-efficient low-emission public transport programme | Priority | Scheme | Not started |  | Local municipalities | Estonia, Tallinn | 29200000 | 29200000 | 14600000 | 14600000 | 0 | 0 | 0 | N/A | 0 | 37680 MWh | 0 | 12000 tCO2 | N/A | N/A | 0 | N/A | Yes, 2023 | The need to purchase electric buses stems from the objective of prioritizing the development of clean public transport solutions and the obligations imposed on Member States by Directive (EU) 2019/1161 of the European Parliament and of the Council amending Directive 2009/33/EC on the promotion of clean and energy efficient road transport vehicles. Electric buses will be used to operate Tallinn city lines within the framework of a public service obligation imposed by the City of Tallinn as a competent authority under the Public Transport Act on the basis of a public service contract concluded with a service provider pursuant to Regulation 1370/2007. | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Energy-efficient low-emission public transport programme | Priority | Scheme | Tender ongoing |  | Estonian State Fleet | Estonia, Hiiumaa, Saaremaa County | 40000000 | 40000000 | 25400000 | 25400000 | 0 | 0 | 0 | 0 | 0 | 111000 MWh | 0 | 231000 tCO2 | N/A | N/A | 0 | N/A | Yes, 2023 | All feasibility study works (stage one of extended concept design) have been performed and discussed between service provider and contracting authority, including involvement of all stakeholders. In total, 6 prototypes were presented for further development during the next stage of extended concept design. All extended concept design works (stage two) are performed, delivered and discussed between service provider and contracting authority, including involvement of all stakeholders. Hydrogen-battery ferry prototype has been presented and accepted by Contracting authority with readiness for further public procurement of engineering and construction and for relevant basic design and construction. Certain fine tuning of the documents and owners’ remarks are performed together with classification society concept design review and “approval in principle”. Classification society has done concept design review and issued relevant “approval in principle” in December 2023 as the last part of the extended concept design works. Mentioned Classification society services were procured separately by open public procurement. Procurement documents for the basic design and construction of the hydrogen-battery ferry itself are updated and published in the Public Procurement Registry in December 2023, Call for proposals is initiated. Relevant open public procurement is international and complex due to the technical nature and complexity of the project. This has been taken into account in plans for further development of the project. | 2026-10-01 | N/A | N/A | N/A | N/A | N/A
6
7
8
9
10
11
XX
Note on T7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The applicant has to present data on the calculations of changes in energy use (including the annual total energy savings achieved as a result of the project and the expected cumulative energy savings during the economic life of the energy efficiency works) and calculations of the forecast of the reduction of greenhouse gas emissions as a result of the implementation of the project (including the annual reduction of greenhouse gas emissions that can be achieved as a result of the implementation of the project and the expected cumulative reduction of greenhouse gas emissions during the economic life of the energy efficiency works). The calculations must be made by a certified energy efficiency specialist. After the implementation of the project the energy use calculations of the building used by the central government unit will be prepared based on the heat and electricity requirement resulting from the limit of the achievable energy efficiency figure in the typical use of the building.
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The applicant has to present data on the calculations of changes in energy use (including the annual total energy savings achieved as a result of the project and the expected cumulative energy savings during the economic life of the energy efficiency works) and calculations of the forecast of the reduction of greenhouse gas emissions as a result of the implementation of the project (including the annual reduction of greenhouse gas emissions that can be achieved as a result of the implementation of the project and the expected cumulative reduction of greenhouse gas emissions during the economic life of the energy efficiency works). The calculations must be made by a certified energy efficiency specialist. After the implementation of the project the energy use calculations of the building used by the central government unit will be prepared based on the heat and electricity requirement resulting from the limit of the achievable energy efficiency figure in the typical use of the building.

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Programme for improvement of energy efficiency and renewable energy use in public sector buildings MF 2021-2 EE 0-001 Phase 1 | Ministry of Finance in cooperation with Ministry of Regional Affairs and Agriculture | Estonia | 170000000 | The programme is considered a priority scheme under article 10d of the ETS Directive. The objectives include, in addition to considerable energy efficiency improvement, reduction of greenhouse gas (and other) emissions related to the use of public sector buildings, and improvement of the „interior climate“ of the buildings (in relation to positive health impact). | National assessment completed in 2021, updated in 2022 and 2023 and 2024: the scheme does not involve granting State aid (in the meaning of Article 107(1) of the Treaty on the Functioning of the European Union). | € 170 000 000, remaining amount to be disbursed € 60 427 600 | National energy and climate plan 2030; Building renovation strategy of Estonia; Energy Sector Development Strategy 2030 | N/A
2 | Programme for improvement of energy efficiency and renewable energy use in public sector buildings MF 2024-1 EE 0-001 Phase 2 | Ministry of Finance in cooperation with Ministry of Regional Affairs and Agriculture | Estonia | 250000000 | The programme is considered a priority scheme under article 10d of the ETS Directive. The objectives include, in addition to considerable energy efficiency improvement, reduction of greenhouse gas (and other) emissions related to the use of public sector buildings, and improvement of the „interior climate“ of the buildings (in relation to positive health impact). | National assessment completed in 2024: the scheme does not involve granting State aid (in the meaning of Article 107(1) of the Treaty on the Functioning of the European Union). | € 250 000 000, remaining amount to be disbursed € 248 285 715 | National energy and climate plan 2030; Building renovation strategy of Estonia; Energy Sector Development Strategy 2031 | N/A | 2016 | Working groups, documents were up for public commenting in EIS (https://eelnoud.valitsus.ee). | 35 energy-field related organisations and companies taking part in Energy Council (created by Ministry of Economics and Comunications) working groups. |  | The Programme is based on the relevant national long-term strategic documents: the Energy Energy Sector Development Plan 2030 (ENMAK 2030) (https://www.mkm.ee/en/energy-sector-and-mineral-resources/energy-economy/energy-sector-development-plan)andtheMobility and Transport Development Plan 2035 (https://kliimaministeerium.ee/likuvus/transpordi-tulevik ). The Programme is designed for implementation of the priority measures identified as part of the strategic development plan (incl. measure 2.4 "Improvement of energy efficiency of the existing buildings stock" and measure 2.5 "Improvement of energy efficiency of the new buildings stock". The public consultation process held during the development process of Energy Sector Development Plan 2030 is described in Chapter 9 of the Explanatory Note to the Development Plan (https://energiatalgud.ee/sites/default/files/images_sala/0/04/ENMAK_2030._Eeln%C3%B5u_seletuskiri_10.10.2016.pdf).
3 | Energy-efficient low-emission public transport programme MF 2021-2 EE 0-002 Phase 1 | Ministry of Climate | Estonia | 159200000 | The programme is considered a priority scheme under article 10d of the ETS Directive. The programme primarily focuses on supporting investments necessary for accelerating and reaching energy efficiency targets set in transport sector and, as a secondary objective, taking into use renewable energy sources suitable for the specific use in public transport. | National assessment completed in 2021, updated in 2022, 2023 and 2024: the scheme does not involve granting State aid (in the meaning of Article 107(1) of the Treaty on the Functioning of the European Union). | € 130 000 000, remaining amount to be disbursed € 66 082 368 | National energy and climate plan 2030; Transport and Mobility Master Plan 2021-2035 | N/A
4 | Energy-efficient low-emission public transport programme Phase 2 | Ministry of Climate | Estonia | 115000000 | The programme is considered a priority scheme under article 10d of the ETS Directive. The programme primarily focuses on supporting investments necessary for accelerating and reaching energy efficiency targets set in transport sector managed by the local authorities and, as a secondary objective, taking into use renewable energy sources suitable for the specific use in public transport. Specific content is being further specified . | National assessment completed in 2024: the scheme does not involve granting State aid (in the meaning of Article 107(1) of the Treaty on the Functioning of the European Union). | 115000000 | National energy and climate plan 2030; Transport and Mobility Master Plan 2021-2036 | N/A | 2016 | Working groups, documents were up for public commenting in EIS (https://eelnoud.valitsus.ee). | 35 energy-field related organisations and companies taking part in Energy Council (created by Ministry of Economics and Comunications) working groups. |  | The Programme is based on the relevant national long-term strategic documents: the Energy Energy Sector Development Plan 2030 (ENMAK 2030) (htfps://www.mkm.ee/en/energy-sector-and-mineral-resources/energy-economy/energy-sector-development-planandtheMobility and Transport Development Plan 2035 (https://kliimaministeerium.ee/likuvus/transpordi-tulevik ). The Programme is designed for implementation of the priority measures identified as part of Mobility and Transport Development Plan 2035 (target 7.1. „Efficiently organised public transport at high quality level"') The public consultation process held during the development process of Energy Energy Sector Development Plan 2030 is described in Chapter 9 of the Explanatory Note to the Development Plan (https://energiatalgud.ee/sites/default/files/images_sala/0/04/ENMAK_2030._Eeln%C3%B5u_seletuskiri_10.10.2016.pdf).
5
6
7
8
9
10
11
XX

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia