## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2023 | Croatia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF-2021-2-HR-0-002 | n.a. | Energy efficiency improvement and generation of electricity from renewable sources of the Dilj production plants | Priority | Project | Construction ongoing | n.a. | Dilj d.o.o. (Ltd.), Vinkovci, Ciglarska 33 | Vinkovci, Ciglarska 33 Našice, Braće Radić 200 | 5430449.2375 | 4344359.39 | 2148853.27 | 2148853.27 | 2148853.27 | 1915872.33 | n.a. | n.a. | n.a. | 8737 | n.a. | 129756 | n.a. | 2.31 | n.a. | 41.8512 | YES, 2020 | The project activity of investing in the energy efficiency of replacing the wheel mill has been completed. Other project activities are nearing the end of implementation, waiting for the regular overhaul of the plant so that they can be completed to the end. The project activity of RES (photovoltaic power plants) is nearing its end and its completion is expected in May 2024. | 45536 | Slight delay to project implementation was due to prolonged contracting procedure as this was the first investment form the MF. | There are no xpected changes in eligible costs, technology applied or results of investment. | n.a. | n.a. | n.a.
2 | MF-2022-1-HR-0-001 | MF-2022-2-HR-0-005 MF 2023-1 HR 0-002 | State Aid Scheme to support the production of electricity from renewable energy sources from the Modernisation fund | Priority | Scheme | Tender ongoing | https://mingor.gov.hr/o-ministarstvu-1065/djelokrug/uprava-za-klimatske-aktivnosti-1879/modernizacijski-fond/9095 | Look at Sheet Final beneficiary&Location | Look at Sheet Final beneficiary&Location | 100000000 | 80000000 | 80000000 | 80000000 | 42226812.16 | 0 | n.a. | n.a. | n.a. | 1337827.7 | n.a. | 213372.9 | n.a. | 85.1 | n.a. | n.a. | NO (in Investment overview submitted in 2021 the information was given for the possible projects, but not the scheme within which the projects would be financed) | The call for proposals within the scheme was published in April 2023 with the budget of 60 mil Euro, the results were published in November 2023, and the contracts with the selected final recipients of MF support were sign in December 2023, awarding 42 mil euros to 160 projects. The second call for proposals within the scheme will be published in Q2 2024 with the remaining amount from MF, and the contract award is expected in December 2024. | n.a. | There is a slight delay in initial implementation of the scheme, namly publication of the first call for proposals, that has been overcome in meantime and the project implementation is proceeding without delay. The second call for proposals is expected to be published and contract award finalized by the end of 2024. | n.a. | n.a. | n.a. | n.a.
3 | MF-2022-2-HR-0-004 | n.a. | GRID SCALE SMART ENERGY STORAGE | Priority | Project | Not started | n.a. | IE-Energy d.o.o., Rijeka, Korzo 40 | Šibenik 43°42´32.5"N 15°54´59.6"E | 75000000 | 60000000 | 19800000 | 19800000 | n.a. | n.a. | n.a. | n.a. | n.a. | 165000 | n.a. | 108101 | n.a. | n.a. | n.a. | n.a. | YES, 2020 | All permits obtained and designes are completed. Preparation for signing contract with MESD and National Fund. | 2025-12-31 | For now, delays are not expected. | n.a. | n.a. | n.a. | n.a.
4 | MF-2022-2-HR-0-002 | MF 2023-1 HR 0-001 | State aid Scheme to support the investments in energy efficiency improvement from the Modernisation Fund | Priority | Scheme | Not started | https://mingor.gov.hr/o-ministarstvu-1065/djelokrug/uprava-za-klimatske-aktivnosti-1879/modernizacijski-fond/9095 | n.a. | n.a. | 100000000 | 80000000 | 80000000 | 80000000 | n.a. | n.a. | n.a. | n.a. | n.a. | 2360000 | n.a. | 2162000 | n.a. | n.a. | n.a. | 74.0056 | NO (in Investment overview submitted in 2021 the information was given for the possible projects, but not the scheme within which the projects would be financed) | The propositions of the call for proposals were prepared in collaboration with Croatian Energy institute Hrvoje Požar, and are to be published for consultation with the project promoters. The call for proposals within the scheme will be published in Q2 2024 and the contract award is expected in December 2024. | n.a. | The propositions of the call for proposals were prepared in collaboration with Croatian Energy institute Hrvoje Požar, and are to be published for consultation with the project promoters, with a delay in regard to initial timeschedule. The first call for proposals was planned in 2023, and due to delays the scheme will be implemenated as one call for proposals, to be published in Q2 2024 and the contract award is expected in December 2024. | n.a. | n.a. | n.a. | n.a.
5 | MF 2023-1 HR 0-003 | n.a. | PV and energy storage for the public water service providers | Priority | Scheme | Not started | https://mingor.gov.hr/o-ministarstvu-1065/djelokrug/uprava-za-klimatske-aktivnosti-1879/modernizacijski-fond/9095 | n.a. | n.a. | 87500000 | 70000000 | 70000000 | 23000000 | n.a. | n.a. | n.a. | n.a. | n.a. |  | n.a. | 15200 | n.a. | 78 | n.a. | n.a. | No | The first call for proposals within the scheme will be published in Q2 2024 and the contract award is expected in Q1 2025. The propositions of call for proposals are in consultation procedure with the project promoters. | n.a. | There is a delay in initial implementation of the scheme, namly publication of the first call for proposal, as there were changes in sectoral legislation regulating the future final beneficieries of the support, as well as changes to the GBER regulation that need to be incorporated into the scheme. Furthermore, the nationaly funded scheme for preparation of neccesary documentation for project preparation has been prolonged impacting the project preparation timetable. The propositions of call for proposals are in consultation procedure with the project promoter, the first call for proposals is expected to be published in Q2 2024 and contract award finalized in Q1 2024, followed by the second call for proposals in 2025. | n.a. | n.a. | n.a. | n.a.
6 | MF 2023-1 HR 0-004 | n.a. | Investment in OIE for public municipal waste service providers | Priority | Scheme | Not started | https://mingor.gov.hr/o-ministarstvu-1065/djelokrug/uprava-za-klimatske-aktivnosti-1879/modernizacijski-fond/9096 | n.a. | n.a. | 12500000 | 10000000 | 10000000 | 5000000 | n.a. | n.a. | n.a. | n.a. | n.a. | MINGOR | n.a. | 1800 | n.a. | 5 | n.a. | n.a. | No | The first call for proposals within the scheme will be published in Q2 2024 and the contract award is expected in Q1 2025. | n.a. | There is a delay in scheme implemantation, as the first call for proposals were expected in 2023, together witht the call for proposals for public water service provider. The schemes were planned to be implemented in paralel, and as such the call for proposal is expected to be published in Q2 2024 and contract award finalized in Q1 2024, followed by the second call for proposals in 2025. | n.a. | n.a. | n.a. | n.a.
7
8
9
10
11
XX

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Heating and cooling in manufacturing industry | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 80 mil € 2024.-2025. Total cost=total scheme volume | The investment proposal is for a priority scheme for generation and use of thermal energy for self consumption for manufacturing industry in Croatia, where support will be given for construction of RES instalations for heat production and energy efficiancy measures in heat production at manufacturing plants. | pending | 80 mil € 2024.-2025. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions and increasing the share of renewable energy in final energy consumption, as well as energy efficiency objectives. | n.a.
2 | Investment in low-emission transport | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 100 mil €- road 2024-2025 40 mil €-railway 2025 Total cost=total scheme volume | The investment proposal will be for a priority scheme for incentivizing and supporting deployment of clean vehicles (electric and/or H2) in public and private vehicles and deployment of battery trains in Croatia. | pending | 100 mil €- road 2024-2025 40 mil €-railway 2025 | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions as well as energy efficiency objectives in transport sector. | n.a.
3 | Use of geothermal energy in destrict heating network | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 90 mil € 2026. i 2027. Total cost=total scheme volume | The investment proposal will be for priority scheme for use of geothermal energy for production of energy for heat production in the existing district heating networks with aim of replacing fossil fuels use. | pending | 90 mil € 2026. i 2027. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions and increasing the share of renewable energy in final energy consumption, as well as energy security objectives. | n.a.
4 | Waste to energy | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 60 mil € 2025.-2026. Total cost=total scheme volume | The investment proposal will be for priority scheme for combined heat and power plants from RDF in waste managment centers. | pending | 60 mil € 2025.-2026. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions and increasing the share of renewable energy in final energy consumption, as well as energy efficiency and energy security objectives. | n.a.
6 | Construction of 400KW transmission network | Croatian Transmission System Operator | HR 02 HR 03 HR 05 HR 07 | 800 mil € | The investment proposal would be a priority project for constrution of 400kW transmission network in order to enable introduction of RES in the grid. | n.a. | 502 mil € | The projet contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation and internal energy market, enabling further incorporation of renewable energy sources in the energy system. | n.a.
7 | Use of RES in industry | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 50 mil € | The investment proposal is for priority scheme for RES for self consumption for manufacturing industry in Croatia, where support will be given for construction of RES instalations at manufacturing plants. | pending | 50 mil € 2027. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions and increasing the share of renewable energy in final energy consumptions. | n.a.
8 | Energy efficiency with ODS removal | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 06 | 35 mil € Total cost=total scheme volume | The investment proposal is for a priority scheme for energy efficieny measure targeting the replacement of equipment with ODS (prior to 2015) with new equipment working with natural refrigerants. | pending | 35 mil € 2025. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions as well as energy efficiency dimention. | n.a.
9 | Energy efficieny in modernisation of transmission network | Ministry of Economy and Sustainble Development ( together with Environmental Protection and Energy Efficiency Fund) | HR 02 HR 03 HR 05 HR 07 | 40 mil € 2028. Total cost=total scheme volume | The investment proposal is for a priority scheme for energy efficieny measure targeting the modernisation of transmission network | pending | 40 mil € 2028. | Scheme contributes to Integrated National Energy and Climate Plan for the Republic of Croatia for the period 2021-2030 (NECP), in particular in regard to decarbonisation, with reducing the GHG emissions and increasing the share of renewable energy in final energy consumption, as well as energy security objectives. | n.a.

## Final beneficiary&Location
Number | Final beneficiary of the support within scheme MF-2022-1-HR-0-001 | Location of the investment for scheme MF-2022-1-HR-0-001
1 | BONAVIA d.o.o. | 31207 TENJA, Osječka 190
2 | Haix obuća d.o.o. | 40320 MALA SUBOTICA, Gospodarska 1
3 | SEKLO d.o.o. | 35410 NOVA KAPELA, Bili Brig 3
4 | DIN d.o.o. | 10315 NOVOSELEC, Park hrvatskih mučenika 4
5 | CriDan d.o.o. | 42208 CESTICA, 8. maja 46
6 | ENDI LINE d.o.o. | 10380 SVETI IVAN ZELINA, Zagrebačka ulica 60
7 | MLINČEK j.d.o.o. | 48260 KRIŽEVCI, Ulica Nikole Tesle 40
8 | MAGEL d.o.o. | 44250 MALA GORICA, PETRINJA, Mala Gorica 31
9 | Zagrebačka pivovara d.o.o. | 10290 ZAPREŠIĆ, Ruševje 4
10 | DAMIDA STIROPOR d.o.o. | 21232 PRISOJE , Prisoje bb
11 | BRAVAR-MONT d.o.o. | 35210 VRPOLJE , Ivana Meštrovića 37
12 | MARIN EXPERT d.o.o. | 21204 DUGOPOLJE, Zagrebačka 22
13 | PASTOR - TVA - d.d. | 10437 RAKITJE, Novačka cesta 2
14 | MUNDUS VIRIDIS d.o.o. | 10345 GRADEC, Grabrić 17
15 | Modepack d.o.o. | 10410 VELIKA GORICA, Ulica Fausta Vrančića 33
16 | KOSTWEIN - PROIZVODNJA STROJEVA d.o.o. | 42000 VARAŽDIN, Podravska ulica 37
17 | Gumiimpex - GRP d.o.o. | 42202 TRNOVEC BARTOLOVEČKI, Gospodarska ulica 9
18 | LEPIRAC d.o.o. | 43000 BJELOVAR, Lepirac 1
19 | HLAD USLUGE d.o.o. | 35000 SLAVONSKI BROD, Ulica Ferde Filipovića 59F
20 | ORAH d.o.o. | 47280 OZALJ, Mali Erjavec 55
21 | MLINAR pekarska industrija d.o.o. | 31000 OSIJEK, Martina Divalta 322
22 | MLINAR pekarska industrija d.o.o. | 22000 ŠIBENIK, Bana Josipa Jelačića 13
23 | MLINAR pekarska industrija d.o.o. | 10000 ZAGREB, Radnička cesta 228c
24 | DOK-ING d.o.o. | 10000 ZAGREB, Slavonska avenija 24/6
25 | Meteor Grupa - Labud d.o.o. | 10000 ZAGREB, Radnička cesta 173 R
26 | Pag 91 d.o.o. | 51219 ČAVLE, Soboli bb
27 | USLUGA d.o.o. | 34555 PAKRAC, Gornja Obrijež 74A
28 | Naturalis d.o.o. | 22310 CIVLJANE, Ivetići 1
29 | STIL-PEKARNA d.o.o. | 10257 ZADVORSKO, Zadvorska Ulica II. Odvojak 7
30 | SINAGO d.o.o. | 49243 OROSLAVJE, Mokrice 180D
31 | OBLAK BETON d.o.o. | 22221 RADONIĆ, Obrtnička ulica 1A
32 | IVANČICA d.d. | 42240 IVANEC, Ulica Petra Preradovića 11
33 | GORICA STAKLO d.o.o. | 10419 RAKITOVEC, Rakitovec 441,443,447
34 | Heplast-pipe d.o.o. | 40323 PRELOG, Ulica kralja Zvonimira 38
35 | KAVRAN GRUPA d.o.o. | 40000 ČAKOVEC, Kalnička 63
36 | MODERATOR d.o.o. | 53234 UDBINA, Podudbina 15
37 | Ducati komponenti d.o.o. | 42230 LUDBREG, Ulica Branitelja Domovinskog rata bb
38 | OMIAL NOVI d.o.o. | 21310 OMIŠ, Zakučac 11
39 | Luki drvo d.o.o. | 44330 NOVSKA, Osječka ulica 178A
40 | KONČAR- Energetika i usluge d.o.o. | 10000 ZAGREB, Fallerovo šetalište 22
41 | ROTOPLAST d.o.o. | 10431 KERESTINAC, Poduzetnička 7
42 | VEGA A.T.S. d.o.o. | 52466 NOVIGRAD, Ulica Rijeke Dragonje 12
43 | ALUFLEXPACK NOVI d.o.o. | 23241 POLIČNIK, Ulica dr. Franje Tuđmana 25
44 | SAVA d.o.o. | 35435 STARA GRADIŠKA, Trg hrvatskih branitelja 1
45 | TMT d.o.o. | 42000 VARAŽDIN, Ivana Severa 2A
46 | HIPP CROATIA d.o.o. | 44400 GLINA, Ulica Kralja Zvonimira 1
47 | RETA d.o.o. | 47000 KARLOVAC, Zagrebačka 15K
48 | Lošinjska plovidba - Brodogradilište d.o.o. | 51550 MALI LOŠINJ, Ul. Lošinjskih brodograditelja 55
49 | REVISO d.o.o. | 44272 LEKENIK, Zagrebačka ulica 157
50 | Euro Reflex d.o.o. | 31000 OSIJEK, Vukovarska 219A
51 | Čateks d.d. | 40000 ČAKOVEC, Zrinsko-Frankopanska 25
52 | BADEL 1862 d.d. | 10000 ZAGREB, Ulica grada Gospića 7
53 | ZEKIĆ d.o.o. | 51216 VIŠKOVO, Blažići 23
54 | INOXMONT-VS - d.o.o. | 42230 SIGETEC LUDBREŠKI, Ulica Miroslava Krleže 2
55 | DUE-DI d.o.o. | 49246 MARIJA BISTRICA, Tugonica 60
56 | Eonex d.o.o. | 42202 TRNOVEC , Gospodarska ulica 6
57 | AB PRODUKT d.o.o. | 47000 KARLOVAC, Mala Švarča 209
58 | Cro-go d.o.o. | 21210 SOLIN, Ulica don Frane Bulića 64
59 | VARGON d.o.o. | 51227 KUKULJANOVO, Kukuljanovo 352
60 | DRVODJELAC d.o.o. | 42250 LEPOGLAVA, Hrvatskih Pavlina 84
61 | GRAFIČAR TVORNICA VREĆA I TISKARNICA d.o.o. | 48000 KOPRIVNICA, Borovljani 8G
62 | GRAFIČAR d.d. | 42230 LUDBREG, Frankopanska ulica 89
63 | A.M.S. - BIOMASA d.o.o. | 33000 VIROVITICA, Ulica Antunovac 11
64 | Željko Kranjčec, vlasnik obrta "OBRT POGREBNA OPREMA " | 43270 VELIKI GRĐEVAC, Stjepana Radića 2A
65 | KONČAR-ELEKTRIČNA VOZILA d.d. | 10090 ZAGREB, Ulica Ante Babaje 1
66 | HOTO LIGNUM d.o.o. | 42222 LJUBEŠĆICA, Poduzetnička zona Ljubešćica, Gospodarska ulica 8
67 | T.B.S. - Tvornica betonskih stupova d.o.o. | 10450 JASTREBARSKO, Novaki Petrovinski 100
68 | Sambi d.o.o. | 43000 BJELOVAR, Hratskog proljeća 1
69 | Auric timber d.o.o. | 33520 SLATINA, Industrijska 6
70 | CENTROMETAL d.o.o. | 40306 MACINEC, Glavna ulica 12
71 | GALEB DALMATINSKA TRIKOTAŽA d.d. | 21310 OMIŠ, Mosorska cesta 15
72 | Vetropack Straža d.d. | 49231 HUM NA SUTLI, Hum na Sutli 203
73 | FACC Solutions Croatia d.o.o. | 10297 JAKOVLJE, Jakovljanska ulica 31
74 | MURAPLAST d.o.o. | 40329 KOTORIBA, Sajmišna 16
75 | Miljenko Vinski, vlasnik obrta "VINSKI JURAJ ALATI" | 47000 KARLOVAC, Zagrebačka 94
76 | KONČAR - Aparati i postrojenja d.o.o. | 10000 ZAGREB, Borongajska cesta 81C
77 | Tvornica plinskih turbina d.o.o. | 47000 KARLOVAC, Mala Švarča 195
78 | OPG DARIO CENGER | 43531 MASLENJAČA, Velika Maslenjača BB
79 | PRO WOOD d.o.o. | 31511 ĐURĐENOVAC, Trg Franje Tuđmana 1
80 | PPS GALEKOVIĆ d.o.o. | 10410 MRACLIN, Braće Radića 199A
81 | ISKRA brodogradilište 1 d.o.o. | 22000 ŠIBENIK, Obala Jerka Šižgorića 1
82 | KOTLAR d.o.o. | 48350 ĐURĐEVAC, Ulica grada Vukovara 10
83 | KONČAR - Distributivni i specijalni transformatori d.d. | 10000 ZAGREB, Josipa Lončara 9 i 9A
84 | DI ČAZMA d.o.o. | 43240 GRAD ČAZMA, Alojza Vulinca 28
85 | ISKRA ZELINA KEMIJSKA INDUSTRIJA d.o.o. | 10380 SVETI IVAN ZELINA, Fučkani 6
86 | ATLANTIC CEDEVITA d.o.o. | 48260 APATOVEC, Brežanci 91
87 | OPREMA d.d. | 42230 LUDBREG, GOSPODARSKA ULICA 5
88 | LIPA d.o.o. | 42220 NOVI MAROF, Varaždinska ulica 90
89 | Inkop International d.o.o. | 49222 POZNANOVEC , Ulica Zagorske brigade 1
90 | Predrag Banda, vlasnik obrta "EUROPLAST" | 31540 DONJI MIHOLJAC, Vukovarska 142
91 | Hittner d.o.o. | 43000 BJELOVAR, Pakračka ulica 10
92 | Hilding Anders d.o.o. | 40323 PRELOG, Ulica kralja Zvonimira 38
93 | VIPLAST d.o.o. | 42000 VARAŽDIN, Kućanska 22
94 | Tiskara Reprint d.o.o. | 10360 SESVETE, ZAGREB, Rimski put 11E
95 | BMD STIL d.o.o. | 49282 KONJŠČINA, Pešćeno bb
96 | PAP-PROMET d.o.o. | 10431 SVETA NEDJELJA, dr. Franje Tuđmana 77
97 | Jelen Professional d.o.o. | 40319 BELICA, Braće Radić 37A
98 | MIAZ- IVANČIĆ d.o.o. | 49246 ZLATAR, Ulica Silvija Strahimira Kranjčevića bb
99 | Istra Apparatus d.o.o. | 52333 POTPIĆAN, Industrijska 1
100 | SAB d.o.o. | 43500 DARUVAR, Petra Preradovića 108 i 110
101 | Simplex d.o.o. | 35208 GORNJA VRBA, Sjeverna ulica 17
102 | MEDITA d.o.o. | 23241 POLIČNIK, GRABI 12
103 | PARKETI ARAMBAŠIĆ d.o.o. | 34310 PLETERNICA, Požeška Koprivnica 14
104 | Sincro d.o.o. | 51227 KUKULJANOVO, Kukuljanovo 385 385
105 | SUNTEC d.o.o. | 40000 PRIBISLAVEC, Industrijska ulica 46
106 | FED d.o.o. | 10372 RUGVICA, Dugoselska ulica 1e
107 | FERROSTIL MONT d.o.o. | 49210 ZABOK, Prilaz dr. Franje Tuđmana 111
108 | AUTO KUĆA BEBIĆ d.o.o. | 21210 SOLIN, 21210 38D
109 | CEMIX CROATIA d.o.o. | 48350 ĐURĐEVAC, Petra Preradovića 51
110 | BELUPO d.d. | 48000 KOPRIVNICA, Danica 5
111 | Recom d.o.o. | 10000 ZAGREB , Kamenarka 33
112 | LEIER-LEITL D.O.O. | 42204 TURČIN, Zagrebačka 89
113 | FRAGMAT H d.o.o. | 49223 SVETI KRIŽ ZAČRETJE, Donja Pačetina 1A
114 | KONČAR - Metalne konstrukcije d.o.o. | 10000 ZAGREB, Fallerovo Šetalište 22
115 | Klimaoprema d.d. | 10430 SAMOBOR, Gradna 78a
116 | SPIRAL PIPES TECHNICS d.o.o. | 21270 ZAGVOZD, DR. FRANJE TUĐMANA 63
117 | BAJKMONT d.o.o. | 44000 SISAK, Ognjena Price 11
118 | Jedinstvo Kartonaža d.o.o. | 42240 IVANEC, Rudarska 6
119 | TVORNICA DOBRE HRANE d.o.o. | 33000 VIROVITICA, Industrijska ulica I 1
120 | HANJES d.o.o. | 42202 TRNOVEC, Gospodarska ulica 10
121 | PRIMABIRO d.o.o. | 40000 ČAKOVEC, Zrinsko-Frankopanska ulica 23
122 | TISKARA ZAGREB D.O.O. | 10000 ZAGREB, RADNIČKA CESTA 210
123 | Sobočan d.o.o. | 40315 MURSKO SREDIŠĆE, Slatine 18
124 | M.I. Hršak d.o.o. | 44000 SISAK, Božidara Adžije 2
125 | Kircek d.o.o. | 42222 LJUBEŠĆICA, Ivanovo Polje 1B
126 | BENETTON TEKSTIL D.O.O. | 31000 OSIJEK, VUKOVARSKA CESTA 219A
127 | Spiroflex d.o.o. | 35208 RUŠČICA, Ljudevita Gaja 7
128 | Fusio d.o.o. | 52440 BUIĆI , Buići 60
129 | Ferokotao d.o.o. | 40320 DONJI KRALJEVEC, Kolodvorska ulica 78a
130 | GPI Istra d.d. | 52352 KANFANAR, Burići 9a
131 | STANIĆ d.o.o. | 10000 ZAGREB, Slavonska avenija 22 i 22AA
132 | K.D.S. Valentak d.o.o. | 10370 GRAČEC, Zagrebačka ulica 105
133 | KANDIT d.o.o. | 31000 OSIJEK, VUKOVARSKA CESTA 239
134 | EDILTEC d.o.o. | 42250 LEPOGLAVA, Varaždinska 13
135 | TPK Orometal d.d. | 49243 OROSLAVJE, Milana Prpića 118
136 | Santaj plastika d.o.o. | 31550 VALPOVO, Sunčana 17
137 | Sano d.o.o. | 44317 POPOVAČA, Industrijska cesta 1
138 | TIM Topusko d.o.o. | 44400 TOPUSKO, Školska 35
139 | Semmelrock d.o.o. | 47300 OTOK OŠTARIJSKI, Otok Oštarski 4E
140 | PALFINGER PROIZVODNA TEHNOLOGIJA HRVATSKA d.o.o. | 51300 DELNICE, LUČICE 2A
141 | LEDO plus d.o.o. | 10000 ZAGREB, Marijana Čavića 7
142 | DELTABLOC Components d.o.o. | 40318 TURČIŠĆE, Turčišće 106F
143 | AQUAESTIL PLUS d.o.o. | 47280 OZALJ, Kolodvorska 24B
144 | LOŽ METALPRES d.o.o. | 51303 PLEŠCE, Antuna Muhvića 52
145 | LAGER BAŠIĆ d.o.o. | 10255 DONJI STUPNIK, Trgovačka 3
146 | SAMOBORKA d.d. | 10430 SAMOBOR, Ulica Nikole Šubića Zrinskog 12
147 | SAMOBORKA d.d. | 10430 SAMOBOR, Ulica Nikole Šubića Zrinskog 15A
148 | JAMNICA plus d.o.o. | 10453 GORICA SVETOJANSKA, Celine 54
149 | JAMNICA plus d.o.o. | 10451 PISAROVINA, Vladimira Nazora 57
150 | SAMOBORKA SPLIT d.o.o. | 21203 GORNJI MUĆ, Prisike 19
151 | More d.o.o. | 48214 SVETI IVAN ŽABNO, Kuštani 25
152 | CEMEX Hrvatska d.d. | 21212 KAŠTEL SUĆURAC, Cesta dr. Franje Tuđmana 45
153 | CEMEX Hrvatska d.d. | 10090 ZAGREB, Huzjanova 38
154 | CEMEX Hrvatska d.d. | 21210 SOLIN, Salonitanska 19
155 | Wienerberger d.o.o. | 31400 ĐAKOVO, Nikole Tesle 203
156 | Podravka d.d. | 48000 KOPRIVNICA, Industrijska zona Danica - Ulica Danica; Đelekovečka cesta 6A, 12, 14; 21
157 | Podravka d.d. | 48000 KOPRIVNICA, Ante Starčevića 32
158 | Podravka d.d. | 42000 VARAŽDIN, Biškupečka ulica 60
159 | Podravka d.d. | 21204 DUGOPOLJE, Ul. Bana Josipa Jelačića 16
160 | STS-tech d.o.o. | 40315 MURSKO SREDIŠĆE, Ulica Svetog Josipa Radnika 4

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia