## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2023 | Slovakia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-2 SK 0-001 | Discontinued investment | State Aid Scheme to support the production of electricity from renewable energy sources from the Modernization Fund | Priority | Large-scale scheme |  | https://www.minzp.sk/files/oblasti/politika-zmeny-klimy/ets/schema-st-pomoci-mof_mhsr-eng_f.pdf | - | - | 499999200 | 416666000 | 250000000 | 250000000 | - | - | - | - | - | - | - | - | - | - | - | - | Yes, 2021, 2022. | -
2 | MF 2021-2 SK 0-002 | 1. MF 2022-1 SK 0-003 State Aid Scheme to support the investments to modernise energy systems, including. 2. MF 2023-2 SK 0-001 - State aid scheme to support the investment to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund: high-efficiency cogenerations energy storage and energy efficiency mprovement from the Modernisation Fund: high-efficiency cogenerations. | State Aid Scheme to support the investments to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund: high-efficiency cogenerations | Priority | Large-scale scheme | Construction ongoing | https://www.minzp.sk/files/oblasti/politika-zmeny-klimy/ets/schema-sp-mof-teplarne-final_en.pdf | see the sheet "Beneficiairies" |  | 715200000 | 596000000 | 350000000 | 350000000 | The 8 granting contracts was signed in the toal amount of 51 900 263,42 EUR. |  | - | - | 0 | 3207287.044 | 0 | 657711.426 | 0 | 0 | 0 | 167.5412 | Yes, 2021, 2022, 2023. | The first call under this investment proposal was launched on July 27, 2022 and tha actual status is as follows: 1. Evaluation round: 1 granting contract (for HE CHP activity) was signed with the amount of 14 725 998 EUR. 2. Evaluation round: 4 granting contracts (for HE-CHP activities) were signed with the amount of 27 706 920,47 EUR. Moreover 3 granting contracts for the combination of DHC and HE-CHP activities were signed with the amount of 9 467 344,95 EUR.
3 | MF 2021-2 SK 0-003 | 1. MF 2022-1 SK 0-002 State aid scheme to support the investment to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund – DHC.* 2. MF 2023-2 SK 0-002 - State aid scheme to support the investment to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund - DHC. | State aid scheme to support the investments to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund – DHC | Priority | Large-scale scheme | Construction ongoing | https://www.minzp.sk/files/oblasti/politika-zmeny-klimy/ets/schema-sp-mof-teplarne-final_en.pdf | see the sheet "Beneficiairies" | Komárno, Humenné, Nitra, Topoľčany | 918000000 | 765000000 | 650000000 | 650000000 | The 32 granting contracts were signed in the toal amount of 98 263 333,67 EUR. | 2136982.63 | - | - | 0 | 679861.031 | 0 | 151258.484 | 0 | 0 | 0 | 703.2976 | Yes, 2021, 2022, 2023. | The first call under this investment proposal was launched on July 27, 2022 and the actual status is as follows: 1. Evaluation round: 12 granting contrats (for modernisation of DHC systems) were signed with the total amount of 35 306 971 EUR. 2. Evaluation round: 13 granting contracts were signed with the amount of 51 952 285,48 EUR. Moreover 3 granting contracts were signed with the amount 11 004 077,19 EUR. Total amount paid to the project proponent/final recipients: 761 020,19 EUR.
4 | MF 2022-2 SK 0-002 | - | Scheme State aid scheme for the decarbonisation of industry from the Modernization fund | Priority | Large-scale scheme | Tender ongoing | https://obchodnyvestnik.justice.gov.sk/Handlers/StiahnutPrilohu.ashx?IdPriloha=413728&csrt=16445548320164838832 | https://www.minzp.sk/files/zoznam-schvalenych-prijimatelov-mof.pdf |  | 900000000 | 750000000 | 750 000 000 (Support will be granted based on competitive bidding) | 750 000 000 (Support will be granted based on competitive bidding) | The 5 granting contracts were signed in the toal amount of 140 761 435,94 EUR. | 0 |  |  | 0 | 16472251.84 | 0 | 9276008 | 0 | 57.7 | 0 | 34 | Yes, 2021, 2022, 2023. | The first call under this investment proposal was launched on March 30, 2023. The five granting contracts were signed in the toal amount of 140 761 435,94 EUR (the total elegible costs are 315 423 071 eur).
Note on G6: Administrator: Missing status is: "Discontinued investment"
Note on X9: Administrator: The project envisages the construction of photovoltaic and wind sources (20.5 MW photovoltaics + 37.2 MW wind turbines) of renewable energy with a total output of 57.7 MW, which will supply green energy to an electrolysis unit for the production of green hydrogen with a maximum output of 15 MW.

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Investment support of increasing the energy efficiency of existing public buildings. priority investment | Ministry of Environment of the Slovak Republic | The whole territory of the Slovak Republic | 150000000 | Investment support for aimed at increasing the energy efficiency of existing public buildings - in-depth and multi-stage renovation of buildings, including insulation and heating modernization. The prepration of the scheme will started in 1Q 2024. | not started | 120000000 | measures to increase energy efficiency, especially buildings and industry. chapter 2.2. energy efficiency dimension | no
2 | Investment support of increasing the energy efficiency in households for low-income groups and pensioners in the Slovak Republic. priority investment | Ministry of Environment of the Slovak Republic | The whole territory of the Slovak Republic | 186340000 | Investment support aimed to increase the energy efficiency and reduce greenhouse gas emissions in households of low-income groups and pensioners, by implementing partial renovation of family houses ("Renovation of houses - MINI"). As part of the update of the RepowerEU Program, it was proposed that after the allocation intended for the given measure within the K2 component RepowerEU renovation of family houses has been exhausted, the financing of the mentioned measure will continue from MoF funds in the amount of 186 340 000. | pending | 186340000 | measures to increase energy efficiency, especially buildings and industry. chapter 2.2. energy efficiency dimension | no | 13.3.2023 – 24.3.2023 | Public and interservice consultation on the Draft Amendment to the Recovery and Resilience Plan of the Slovak Republic | the public, experts and other ministries and relevant subjects | One comment received | The comment received: - proposal to revise the definition of the target group (the potential beneficiaries) "Renovation of houses - MINI". Partially accepted - the definition of the targeted group will be the subject of further discussions, and its final form will be decided only during the implementation of the measure.
3 | Gabčíkovo hydroelectric power plant (HPP) priority investment | VODOHOSPODÁRSKA VÝSTAVBA, ŠTÁTNY PODNIK | Trnava region SK021 | 150000000 | Reconstruction and modernization of eight turbogenerators at Gabčíkovo HPP in order to increase energy efficiency: • increasing the safety and reliability of the operation of the turbogenerators of the Gabčíkovo hydroelectric power plant, eliminating technical and moral wear and tear of the equipment and extending the service life of the affected equipment and facilities by at least 30 years, i. until the next overhaul • production of energy from renewable sources • increase of the installed capacity of eight Gabčíkovo turbogenerators, by a total of 20 MW • increase energy efficiency | not started | 150 000 000/30 000 000 | 2. NATIONAL GOALS - 2.1.2. Energy from renewable sources 3. POLICIES AND MEASURES - 3.1.2. Energy from renewable sources | no
4
5
6
7
8
9
10
11
XX
Note on H8: Administrator: Depending on the application of the Block Exemption Regulation or the CEEAG Regulation in the State aid compliance assessment process

## Beneficiaries
Beneficiaries | Organization identification number | Name of the project | Year | Area | Required resources [€] | Approved resources [€] | Status of application | City | SK region
BES s.r.o. | 35752165 | Modernizácia energetických systémov | 2023 | Energetika | 4461079 | 4461079 | Approved | Bratislava IV | Bratislavský
BYTTERM, a.s. | 31584705 | Horúcovodná prípojka pre VS ZŠ V. Javorku 32 Hliny V, Žilina, Vodovodná prípojka - ZŠ V. Javorku, Žilina, Výmenníková stanica v objekte ZŠ V. Javorku 32, Hliny V, Žilina, Výmena vonkajších sekundárnych rozvodov ÚK a TV v tepelnom okruhu VS VŠDS Hliny, Žilina | 2023 | Energetika | 900276.96 | 900276.96 | Approved | Žilina | Žilinský
COM-therm, spol. s r.o. | 36525782 | Centralizácia vykurovania a zvyšovanie energetickej efektívnosti CZT7/3 - Komárno | 2023 | Energetika | 3655700 | 3655700 | Approved | Bratislava II | Bratislavský
ENGIE Services a.s. | 35966289 | Rekonštrukcia sekundárnych rozvodov ÚK, TÚV a cirkulácie OST 3 Brezová pod Bradlom | 2023 | Energetika | 1099369.89 | 1099369.89 | Approved | Bratislava | Bratislavský
Humenská energetická spoločnosť, s.r.o. | 31728812 | Modernizácia a rekonštrukcia rozvodov tepla v Humennom II. etapa | 2023 | Energetika | 5811771 | 5811771 | Approved | Humenné | Prešovský
KMET Handlová, a.s. | 36334634 | Výstavba, rekonštrukcia a modernizácia výroby tepla a rozvodov tepla v meste Handlová | 2023 | Energetika | 13128774 | 13128774 | Approved | Prievidza | Trenčiansky
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia a modernizácia rozvodov centrálneho zásobovania teplom v meste Martin II. etapa | 2023 | Energetika | 4955425 | 4955425 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Nový zdroj tepla a elektrickej energie - plynové motory a transformátor T10 | 2023 | Energetika | 14725998 | 14725998 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Modernizácia nadzemných častí primárnych napájačov SCZT | 2023 | Energetika | 2375741 | 2375741 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | 2. časť - Modernizácia nadzemných častí primárnych napájačov SCZT | 2023 | Energetika | 6107145.93 | 6107145.93 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia HVTS Ľadoveň III. Etapa, Rekonštrukcia HVTS Ľadoveň IV. Etapa, Rekonštrukcia HVTS Ľadoveň V. etapa, Rekonštrukcia HVTS Ľadoveň prepojenie Juh a Ľadoveň, Rekonštrukcia horúcovodu Martin Podháj III. etapa | 2023 | Energetika | 4707493.6 | 4707493.6 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Zdroj KVET v Teplárni A a Zvýšenie parametrov parných kotlov PK1, PK2 | 2023 | Energetika | 7319853.27 | 7319853.27 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia horúcovodného potrubia vetiev Zvolen-Sekier a Zvolen-Zlatý Potok /časť SO 400 HV rozvod Zvolen -Zlatý Potok/ a Akumulácia tepla | 2023 | Energetika | 11654331.93 | 11654331.93 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia horúcovodného potrubia vetiev Zvolen-Sekier a Zvolen-Zlatý Potok - časť SO 500 HV rozvod Zvolen - Podborová | 2023 | Energetika | 969912.38 | 969912.38 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výmena tepelnej izolácie a oplechovania HV potrubí BA východ napájač JUH, Akumulácia tepelnej energie | 2023 | Energetika | 8031006.39 | 8031006.39 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výstavba technológie na vysokoúčinnú kombinovanú výrobu elektriny a tepla ako náhrady za súčasné zdroje v SCZT Západ | 2023 | Energetika | 15000000 | 15000000 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Nová TG1 v závode Martin | 2023 | Energetika | 4107512.82 | 4107512.82 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výstavba technológie na vysokoúčinnú kombinovanú výrobu elektriny a tepla ako náhrady za súčasné zdroje v SCZT Západ - Akumulácia | 2023 | Energetika | 1279554.39 | 1279554.39 | Approved | Bratislava III | Bratislavský
Nitrianska teplárenská spoločnosť, a.s. | 36550604 | Rekonštrukcia a modernizácia rozvodov tepla, domové OST v sústave CZT Nitra - Klokočina a Diely | 2023 | Energetika | 3387129 | 3387129 | Approved | Nitra | Nitriansky
Nitrianska teplárenská spoločnosť, a.s. | 36550604 | Vybudovanie rozvodov tepla, chladu a OST pre obytné domy v sústave CZT Nitra - Chrenová | 2023 | Energetika | 1285343 | 1285343 | Approved | Nitra | Nitriansky
SPRAVBYTKOMFORT, a.s. Prešov | 31718523 | Rekonštrukcia sekundárnych rozvodov OST T-1, OST T-2, OST T-3, OST T-4, OST T-6, OST T-7 vrátane vybudovania 124 ks KDOST | 2023 | Energetika | 7528338.43 | 7528338.43 | Approved | Prešov | Prešovský
STEFE Trnava, s. r. o. | 36277215 | Rekonštrukcia vonkajších sekundárnych rozvodov a modernizácia OST na okruhu Družba 1, Trnava | 2023 | Energetika | 2231150.29 | 2231150.29 | Approved | Trnava | Trnavský
STEFE Trnava, s. r. o. | 36277215 | Rekonštrukcia vonkajších sekundárnych rozvodov a modernizácia OST na okruhu Družba 2, Trnava | 2023 | Energetika | 1687162.07 | 1687162.07 | Approved | Trnava | Trnavský
Teplico, s.r.o. | 31621171 | Modernizácia rozvodov tepla CZT Turčianske Teplice II.etapa - Kuzmányho | 2023 | Energetika | 1559357.02 | 1559357.02 | Approved | Turčianske Teplice | Žilinský
Teplo GGE s. r. o. | 36012424 | Rekonštrukcia a modernizácia rozvodov CZT okruh OST EG 1, 2 Rozkvet, Považská Bystrica | 2023 | Energetika | 2073495.36 | 2073495.36 | Approved | Považská Bystrica | Trenčiansky
Teplárne ZM s.r.o. | 35785225 | Modernizácia energetických systémov | 2023 | Energetika | 2570331 | 2570331 | Approved | Zlaté Moravce | Nitriansky
TERMMING, a.s. | 35972254 | Rekonštrukcia primárneho rozvodu UK medzi šachtou na Brnianskej ul. a OST2 v Malackách | 2023 | Energetika | 584043 | 584043 | Approved | Bratislava III | Bratislavský
TOMA, s.r.o. | 31421695 | Rozšírenie teplovodnej siete TOMA, s.r.o. v meste Topoľčany (tepelné prípojky a OST) | 2023 | Energetika | 702606 | 702606 | Approved | Topoľčany | Nitriansky
Veolia Energia Levice, a.s. | 35968486 | Rekonštrukcia rozvodov okruhu OS86 Levice | 2023 | Energetika | 1553692 | 1553692 | Approved | Bratislava V | Bratislavský
Veolia Energia Levice, a.s. | 35968486 | Rekonštrukcia okruhu OS 46, Rekonštrukcia HVN CZT – Rybníky 5, Levice | 2023 | Energetika | 4352230.92 | 4352230.92 | Approved | Bratislava V | Bratislavský
Veolia Energia Vráble, a.s. | 35802871 | Rekonštrukcia rozvodov ÚK a TÚV sídliska Lúky – Malá strana, Vráble; Realizácia Smart metering sídliska Lúky – Malá strana, Vráble | 2023 | Energetika | 610371.32 | 610371.32 | Approved | Nitra | Nitriansky
Veolia Utilities Žiar nad Hronom, a.s. | 44069472 | Rekonštrukcia výmenníkovej stanice a rozvodov tepla | 2023 | Energetika | 3964111 | 3964111 | Approved | Žiar nad Hronom | Banskobystrický
Veolia Utilities Žiar nad Hronom, a.s. | 44069472 | Modernizácia zdroja VÚ KVET vo Veolia Utilities Žiar nad Hronom, a.s.; Výroba a distribúcia ľadovej vody vo Veolia Utilities Žiar nad Hronom, a.s. | 2023 | Energetika | 5783291.12 | 5783291.12 | Approved | Žiar nad Hronom | Banskobystrický

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia