## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: a) Column N refers to the Modernisation Fund support that EIB disbursed to the beneficiery MS by the cut-off date. b) Column Y (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column U (Greenhouse gas emissions saved in tCO2 - by 31 December of the year preceding report submission). The calculation formula should be shown in the cells. c) Column Z (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column V (Greenhouse gas emissions saved in tCO2 expected cumulative amount by end of the investment lifetime). The calculation formula should be shown in the cells.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2024 | Bulgaria | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2023-1 BG 0-004 | none | Modernisation, digital transformation and development of the information systems and physical infrastructure of the electricity distribution grid in south-eastern bulgaria to enable smart grids for accelerated electrification of transport, storage deployment, de-carbonisation and decentralization of energy consumption and production in distribution grids | Priority | Project | Construction ongoing |  | Electrodistribution yug AD | Bulgaria | 153088459 | 127 573 716 | 31 893 429 | 31 893 429 | 31 893 429 | 0 | 0 | n/a | n/a | 289757 | n/a | 143481 | n/a | n/a | n/a | 1066.9598 | the investment was included in the Annual report for 2022 as well as in the list of investment areas for 2023 | signed contract Dec 2024 | indicative date 2029 | No | No | n/a | consultations carried out with the stakeholders according to the Program and the Internal rules of the Council of ministers | n/a
2 | MF 2023-1 BG 0-003 | none | Modernization and development of the information systems and physical infrastructure of a licensed distribution network operator with the purpose of accelerated electrification and decarbonization of energy consumption and production | Priority | Project | Construction ongoing |  | Electrodistribution North AD | Bulgaria | 36000000 | 30 000 000 | 30 000 000 | 30000000 | 30000000 | 0 | 0 | n/a | n/a | 59987 | n/a | 33260 | n/a | n/a | n/a | 1082.3812 | the investment was included in the Annual report for 2022 as well as in the list of investment areas for 2023 | signed contract Dec 2024 | indicative date 2030 | No | No | n/a | consultations carried out with the stakeholders according to the Program and the Internal rules of the Council of ministers | n/a
3 | MF 2023-1 BG 0-001 | none | Rolling out of smart meters, including necessary infrastructure, stage of the project for integration of advanced metering infrastructure | Priority | Project | Construction ongoing |  | Electrodistribution Grid West EAD (EDG West) | Bulgaria | 36000000 | 30000000 | 30000000 | 30000000 | 30000000 | 0 | 0 | n/a | n/a | 175000 | n/a | 85670 | n/a | n/a | n/a | 420.2171 | the investment was included in the Annual report for 2022 as well as in the list of investment areas for 2023 | signed contract Dec 2024 | indicative date 2027 | No | No | n/a | consultations carried out with the stakeholders according to the Program and the Internal rules of the Council of ministers | n/a
4 | MF 2023-1 BG 0-002 | none | Integration of Metering Data Management (MDM) System, part of Advanced Metering Infrastructure project | Priority | Project | Construction ongoing |  | Electrodistribution Grid West EAD (EDG West) | Bulgaria | 10800000 | 9000000 | 9000000 | 9000000 | 9000000 | 0 | 0 | n/a | n/a | 20000 | n/a | 10400 | n/a | n/a | n/a | 1038.4615 | the investment was included in the Annual report for 2022 as well as in the list of investment areas for 2023 | signed contract Dec 2024 | indicative date 2026 | No | No | n/a | consultations carried out with the stakeholders according to the Program and the Internal rules of the Council of ministers | n/a
| MF 2024-1 BG 0-001 | none | Bulgarian Grid REinforcement ENABLing Full-Fledged Clean Energy Rollout - GREENABLER | Priority | Project | Construction ongoing |  | ESO EAD | Bulgaria | 756971548.8 | 630809624 | 567728662 | 567728662 | 567728662 | 0 | 0 | n/a | n/a | n/a | n/a | 117730646 | n/a | The project is to enable grid conditions to integrate around 4 000 MW new PV and wind capacity | n/a | 6.4297 | the investment was included in the Annual report for 2023 as well as in the list of investment areas for 2024 | signed contract Dec 2024 | indicative date 2031 | No | No | n/a | consultations carried out with the stakeholders according to the Program and the Internal rules of the Council of ministers | n/a

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Heating and cooling from RES | Ministry of energy | Bulgaria | 344444444.44 | Support for heating and cooling from RES | pending | 310000000 | n/a | no | 01-15.11.2024 | online (Ministry of energy website) | representatives of legal enetities, natural persons, NGOs | 11 | positive replies
2 | Zero-emission mobility infrastructure | Ministry of energy | Bulgaria | to be specified | Support for zero-emission mobility infrastructure | n/a | 30000000 | n/a | no | 01-15.11.2024 | online (Ministry of energy website) | representatives of legal enetities, natural persons, NGOs | 3 | positive replies
3 | Non-priority waste-to-energy projects and pilot energy projects and industry innovations | Ministry of energy | Bulgaria | to be specified | Support for non-priority waste-to-energy projects and pilot energy projects and industry innovations | n/a | 70000000 | n/a | no | 01-15.11.2024 | online (Ministry of energy website) | representatives of legal enetities, natural persons, NGOs | 11 | positive replies
4 | Support for low-carbon hydrogen | Ministry of energy | Bulgaria | to be specified | Support for low-carbon hydrogen | n/a | 30000000 | n/a | no | 01-15.11.2024 | online (Ministry of energy website) | representatives of legal enetities, natural persons, NGOs | 4 | positive replies
5 | Support for exploration and exploitation activities for geothermal drilling | Ministry of energy | Bulgaria | 254400000 | Support for exploration and exploitation activities for geothermal drilling | pending | 160000000 | n/a | no | 01-15.11.2024 | online (Ministry of energy website) | representatives of legal enetities, natural persons, NGOs | 4 | positive replies

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia