## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: a) Column N refers to the Modernisation Fund support that EIB disbursed to the beneficiery MS by the cut-off date. b) Column Y (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column U (Greenhouse gas emissions saved in tCO2 - by 31 December of the year preceding report submission). The calculation formula should be shown in the cells. c) Column Z (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column V (Greenhouse gas emissions saved in tCO2 expected cumulative amount by end of the investment lifetime). The calculation formula should be shown in the cells.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2025 | Czechia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | For investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-1 CZ 0-001 | MF 2021-2 CZ 0-003 | Scheme (Part A): Support for photovoltaic power plants with installed capacity up to 1 MW of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Any body based in the Czech Republic and holding a business licence in the energy sector pursuant to Act no. 458/2000 Coll (for more details and exceptions see Annex A). The scheme supports legal entities, municipalities, individuals as well as communities for renewable energy. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 663770000 | 548570000 | 192000000 | 97000000 | 160860510.2589 | 15157830.482 | 0 | NR | 4478.86 | 4522000 | 9591.68 | 3888000 | 1.75 | 452 | 69202.684 | 170.7227 | Yes, 2020, 2021 | 1 call for this programme was launched in 2024, with a total of 1084 projects delivered | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
2 | MF 2021-1 CZ 0-002 | MF 2022-1 CZ 0-008 | Scheme (Part B): Support for photovoltaic power plants with installed capacity above 1 MW of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Any body based in the Czech Republic and holding a business licence in the energy sector pursuant to Act no. 458/2000 Coll. Significant number of projects is expected from electricity generators according to Art. 10c of the Emission Trading Directive, then legal entities outside the EU ETS sector, municipalities, individuals as well as communities for renewable energy. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 3803000000 | 3143000000 | 1100000000 | 313000000 | 546807230.2188 | 8437831.2698 | 0 | NR | 19593.51 | 29588000 | 7495.8 | 25445000 | 8.16 | 2959 | 507350.7831 | 149.4596 | Yes, 2020, 2021 | 1 call for this programme was launched in 2024, with a total of 258 projects delivered | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
3 | MF 2021-2 CZ 0-001 | NR | Scheme (Part A): Modernisation of energy sources priority investments of the Programme “HEAT” | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | C-Energy Planá s.r.o., Veolia Energie ČR, a.s., Veolia Energie Kolín, a.s., Teplárna České Budějovice, a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 657608696 | 543478261 | 250000000 | 30000000 | 64414207.3337 | 47832319.9869 | 0 | NR | 3405.47 | 14438000 | 121487 | 19738000 | 26 | 945 | 5412.9964 | 33.3169 | Yes, 2020 | 1 call for this programme was launched in 2024, with two projects delivered | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
4 | MF 2021-2 CZ 0-002 | NR | Scheme (Part A1): Modernisation of energy production priority investments of the Programme ENERG ETS | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 223586957 | 184782609 | 85000000 | 30000000 | 30000000 | 0 | 0 | NR | 0 | 7937000 | 0 | 10124000 | 0 | 315 | #DIV/0! | 22.0848 | Yes, 2020 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
5 | MF 2022-1 CZ 0-001 | MF 2023-2 CZ 0-010 | Scheme: Modernization of energy sources to natural gas with CHP; priority investment of the Programme “HEAT” (Modernization of thermal energy supply systems) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Veolia Energie ČR, a.s., C-Energy Planá s.r.o., Teplárna Písek, a.s., ČEZ Teplárenská, a.s., CTZ s.r.o., Veolia Průmyslové služby ČR, a.s., | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 499125000 | 412500000 | 198000000 | 100000000 | 60283765.7927 | 26556154.92 | 0 | NR | 0 | 17222000 | 0 | 11460000 | 0 | 0 | #DIV/0! | 43.5537 | Yes, 2020, 2021 | No call was launched in 2024, but 4 projects from previous calls have received a Decision of Minister. | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
6 | MF 2022-1 CZ 0-002 | NR | Scheme: Modernisation of energy sources to natural gas with CHP; priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | BONATRANS GROUP a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 191583333 | 158333333 | 76000000 | 20000000 | 2178556.5456 | 0 | 0 | NR | 0 | 10556000 | 0 | 6550000 | 0 | 0 | #DIV/0! | 29.2494 | Yes, 2020, 2021 | No call has been launched in 2024, but one project have received a Decision of Minister. | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
7 | MF 2022-1 CZ 0-003 | NR | Scheme: Modernisation of energy sources to natural gas with CHP; priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) (P‐5 Modernization of natural gas energy sources with CHP) | Priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 95791667 | 79166667 | 38000000 | 10000000 | 0 | 0 | 0 | NR | 0 | 4722000 | 0 | 960000 | 0 | 0 | #DIV/0! | 99.783 | Yes, 2020, 2021 | NR | NR | The scheme was discontinued. | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
8 | MF 2022-1 CZ 0-004 | NR | Scheme: Municipal PV - small municipalities; priority investment of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Czech small municipalities with less than 3,000 inhabitants. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 161333333 | 133333333 | 100000000 | 50000000 | 98676209.67 | 5895161.4965 | 0 | NR | 5692.89 | 1055000 | 2081.9 | 909000 | 2.32 | 105.7 | 77493.3152 | 177.4844 | Yes, 2021 | 1 call for this programme was launched in 2024, with a total of 567 projects delivered | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
9 | MF 2022-1 CZ 0-005 | NR | Scheme: Municipal PV – communal renewable energy; priority investment of the “RES+” Programme (New renewable energy sources) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Czech municipalities and the entities entirely in public/municipal ownership. | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 484000000 | 400000000 | 200000000 | 100000000 | 26304678.6182 | 181107.0876 | 0 | NR | 0 | 3166000 | 0 | 2727000 | 0 | 317 | #DIV/0! | 177.4844 | Yes, 2021 | 1 call for this programme was launched in 2024, with a total of 208 projects delivered | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | NR | NR
10 | MF 2022-1 CZ 0-006 | NR | Scheme: Modernisation of public lighting; priority investment of the Programme “LIGHTPUB” (Modernization of public lighting systems) | Priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Regions, municipalities, voluntary associations of municipalities, city districts of the capital city of Prague and companies owned by a public entity or operators of public lighting systems. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 53777778 | 44444444 | 40000000 | 10000000 | 5289692.8 | 0 | 0 | NR | 0 | 85000 | 0 | 74000 | 0 | 0 | #DIV/0! | 726.7267 | Yes, 2021 | 1 call for this programme was launched in 2024 and 16 projects were delivered in this call in 2024 | NR | No | NR | The programme document of the LIGHTPUB programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
11 | MF 2022-1 CZ 1-001 | NR | Scheme (Part 1A): Modernization of energy sources to biomass without CHP; non-priority investments of the Programme “HEAT” (Modernization of thermal energy supply systems) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Teplárna Otrokovice a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 623711340 | 515463918 | 250000000 | 50000000 | 67833708.8537 | 2902177.2365 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 2222000 | 0 | 14000000 | 0 | 1240 | #DIV/0! | 44.5508 | Yes, 2020, 2021 | No new call was announced in 2024, but a call announced in 2022 was ongoing. In 2024, 3 projects have received a Decision of Minister. | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
12 | MF 2022-1 CZ 1-003 | NR | Scheme (Part 1C): Modernization of energy sources to natural gas without CHP; non-priority investments of the Programme “HEAT” (Modernization of thermal energy supply systems) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | ČEZ, a. s., Veolia Energie ČR, a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 330000000 | 272727273 | 120000000 | 40000000 | 13372343.9428 | 2099704.8719 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 10556000 | 0 | 15510000 | 0 | 0 | #DIV/0! | 21.2766 | Yes, 2020, 2021 | No call has been launched in 2024. | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
13 | MF 2022-1 CZ 1-004 | NR | Scheme (Part 2A): Modernisation of energy sources to biomass without CHP; non-priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Non-priority | Scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Entities operating the EU ETS installations in the Czech Republic. Based on the analysis of submitted projects intentions, mostly measures on installations in the steel industry, chemical industry, and production of building materials are expected. An updated list of facilities in the EU ETS is published on the website of the Ministry of the Environment. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 82329897 | 68041237 | 33000000 | 10000000 | 0 | 0 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 277000 | 0 | 2540000 | 0 | 160 | #DIV/0! | 32.4133 | Yes, 2020, 2021 | NR | NR | The scheme was discontinued. | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
14 | MF 2022-1 CZ 1-006 | NR | Scheme (Part 2C): Modernisation of energy sources to natural gas without CHP; non-priority investments of the Programme “ENERG ETS” (Improvement of energy efficiency and reductions of emissions of greenhouse gases in EU ETS industry) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Moravskoslezské cukrovary s.r.o. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 244750000 | 202272727 | 89000000 | 25000000 | 3273091.6617 | 1311271.5902 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 6944000 | 0 | 10340000 | 0 | 0 | #DIV/0! | 23.6702 | Yes, 2020, 2021 | No new call was announced in 2024. One project had a contract signed between the beneficiary and the SEF in 2024. | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
15 | MF 2022-1 CZ 1-008 | NR | P-2E: Scheme – Modernization of natural gas energy sources without CHP, ENERG ETS (CZ) Programme | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Slévárny Třinec, a.s., Cukrovar Vrbátky a.s., Tereos TTD, a.s., ORLEN Unipetrol RPA s.r.o., PAPOS Trade s.r.o. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 49500000 | 40909091 | 18000000 | 5000000 | 21675987.5652 | 5135673.5624 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 0 | 1389000 | 0 | 260000 | 0 | 0 | #DIV/0! | 190.3846 | Yes, 2020, 2021 | No new call was announced in 2024. Two projects had a contract signed between the beneficiary and the SEF in 2024. | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
16 | MF 2022-2 CZ 0-001 | MF 2023-2 CZ 0-009, MF 2024-1 CZ 0-012 | Energy Efficiency and Energy Savings in houses and buildings for Residential Sector (HouseEnerg Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Owners of single-family residential houses (as defined by the Act No.283/2021 Coll. Building Act. and owners of the apartment buildings as defined by the Act No. 501/2006. Single-family residential houses and apartment buildings will be used for non-commercial activity. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2904000000 | 2400000000 | 1200000000 | 830000000 | 455379020.955 | 455379020.955 | 0 | NR | 837269.2749 | 16790000 | 213582.4271 | 8003000 | 40.89 | 703 | 13596.6242 | 344.2798 | No | In 2024, 3 new calls were launched under this very successful program. | NR | No | NR | The programme document of the HOUSEnerg programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
17 | MF 2022-2 CZ 0-002 | NR | Improving energy efficiency in industrial production under the EU ETS | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | TŘINECKÉ ŽELEZÁRNY, a. s., Slévárny Třinec, a.s., LASSELSBERGER, s.r.o., Tereos TTD, a.s., Holcim (Česko), a.s., Synthomer a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 1815000000 | 1500000000 | 700000000 | 200000000 | 131858290.8426 | 11423199.8249 | 0 | NR | 0 | 54167000 | 0 | 7089000 | 0 | 0 | #DIV/0! | 256.0305 | Yes, 2020, 2021 | 3 new projects from the previous call had a contract signed between the beneficiary and the SEF in 2024. | NR | No | NR | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
18 | MF 2022-2 CZ 0-003 | NR | Financial instrument for improving energy efficiency in business (ENERG Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Small, medium and large enterprises. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 403333333 | 333333333 | 100000000 | 20000000 | 19247200 | 0 | 0 | NR | 0 | 441000 | 0 | 250000 | 0 | 0 | #DIV/0! | 1613.3333 | Yes, 2021 | NR | NR | No | NR | The programme document of the ENERG programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
19 | MF 2022-2 CZ 1-001 | NR | Renewable Modernisation of Energy Sources for Residential Sector (HOUSEnerg Programme) | Non-priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Owners of single-family residential houses (as defined by the Act No.283/2021 Coll. Building Act. and owners of the apartment buildings as defined by the Act No. 501/2006. Single-family residential houses and apartment buildings will be used for non-commercial activity. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2420000000 | 2000000000 | 1000000000 | 300000000 | 219123245.9797 | 219123246.9798 | 0 | Support for projects approved within the framework of the scheme is provided after the issuance of a decision by the Minister of the Environment and after the conclusion of a grant agreement with SEF CR, which states the amount of support taking into account co-financing from private sources. | 831904.8297 | 83130000 | 275443.9667 | 36199000 | 33 | 2681 | 8785.816 | 66.8527 | No | In 2024, 2 new calls were launched under this very successful program. | NR | No | NR | The programme document of the HOUSEnerg programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
20 | MF 2023-1 CZ 0-001 | NR | Modernization of the ŠKO-ENERGO heating plant | Priority | Project | Tender ongoing | NR | ŠKO-ENERGO, s.r.o. | CZ02 Střední Čechy | 184299843 | 152313919 | 89376476 | 89376476 | 89376476 | 0 | 0 | NR | 0 | 9713661.1111 | 0 | 3648030 | 0 | 190 | #DIV/0! | 50.5204 | Yes, 2022 | NR | 2028-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
21 | MF 2023-1 CZ 0-002 | NR | Modernization of “Brno-North” Heat Source for Brno City Heat Energy Supply System | Priority | Project | Construction ongoing | NR | Teplárny Brno, a.s. | CZ06 Jihovýchod | 147393780 | 121813042 | 79568908 | 79568908 | 79568908 | 27710181.8256 | 0 | NR | 0 | 1699461.1111 | 0 | 377770 | 0 | 43 | #DIV/0! | 390.168 | Yes, 2021, 2022 | NR | 2025-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
22 | MF 2023-1 CZ 0-003 | NR | Modernization of WtE plant of the SAKO Brno to increase processing capacity and operational efficiency | Priority | Project | Construction ongoing | NR | SAKO Brno, a.s. | CZ06 Jihovýchod | 281936597 | 233005452 | 116780718 | 116780718 | 116780718 | 0 | 0 | NR | 0 | 1371205.5556 | 0 | 610080 | 0 | 0 | #DIV/0! | 462.1305 | Yes, 2021, 2022 | NR | 2026-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
23 | MF 2023-1 CZ 0-004 | NR | Construction of WtE facility in the Mělník power plant location | Priority | Project | Tender ongoing | NR | ČEZ, a. s. | CZ02 Střední Čechy | 656427605 | 542502153 | 249946208 | 249946208 | 249946208 | 0 | 0 | NR | 0 | 1344387.7778 | 0 | 467081.1 | 0 | 0 | #DIV/0! | 1405.3825 | Yes, 2021, 2022 | NR | 2027-07-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
24 | MF 2023-1 CZ 0-005 | NR | Scheme: Energy efficiency and savings in modernisation and development of pipelines in the district heating and cooling (DHC) - priority investment of the Programme “HEAT” (Modernization of thermal energy supply systems) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Pražská teplárenská a.s. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 423500000 | 350000000 | 350000000 | 100000000 | 17143359.1423 | 2278895.9857 | 0 | NR | 0 | 16388888.8889 | 0 | 6743000 | 0 | 0 | #DIV/0! | 62.8059 | Yes, 2020, 2021, 2022 | In 2024, no call was launched but 3 project from previous call had a contract signed between the beneficiary and the SEF. | NR | No | NR | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
25 | MF 2023-1 CZ 0-007 | NR | Replacement of a coal block with a gas source (STAGE I) - Opatovice | Priority | Project | Tender ongoing | NR | Elektrárny Opatovice a.s. | CZ05 Severovýchod | 128069377.81 | 105842461 | 64255276 | 64255276 | 64255276 | 0 | 0 | NR | 0 | 1776880.6111 | 0 | 1360641 | 0 | 0 | #DIV/0! | 94.1243 | Yes, 2022 | NR | 2026-05-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
26 | MF 2023-1 CZ 0-008 | NR | Waste to energy plant in Písek | Priority | Project | Tender ongoing | NR | ZEVO PÍSEK s.r.o. | CZ03 Jihozápad | 105987258 | 87592775 | 53864049 | 53864049 | 53864049 | 0 | 0 | NR | 0 | 393420 | 0 | 147370 | 0 | 0 | #DIV/0! | 719.1915 | No | NR | 2028-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
27 | MF 2023-1 CZ 0-009 | NR | The Construction of a steam-gas cycle PPC1 at The UE Komořany | Priority | Project | Tender ongoing | NR | United Energy, a.s. | CZ04 Severozápad | 117208653 | 96866655 | 57784105 | 57784105 | 57784105 | 0 | 0 | NR | 0 | 2984480 | 0 | 2440180 | 0 | 0 | #DIV/0! | 48.0328 | Yes, 2022 | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
28 | MF 2023-1 CZ 0-010 | NR | Waste-to-Energy Facility EVO – Komořany, Most | Priority | Project | Tender ongoing | NR | United Energy, a.s. | CZ04 Severozápad | 249869718 | 206503899 | 105586266 | 105586266 | 105586266 | 0 | 0 | NR | 0 | 1459858.3889 | 0 | 533492.2 | 0 | 0 | #DIV/0! | 468.3662 | Yes, 2022 | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
29 | MF 2023-1 CZ 0-011 | NR | Energy efficiency and energy savings in public buildings (ENERGov Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Public and state entities and their organizations, such as schools, cultural and sports facilities, universities, public research institutions, business companies owned 100% by a public entity, state enterprises, organizational units of the state, state funded organizations, associations, churches, foundations, etc. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 726000000 | 600000000 | 300000000 | 50000000 | 53720 | 0 | 0 | NR | 0 | 760360 | 0 | 247000 | 0 | 0 | #DIV/0! | 2939.2713 | Yes, 2021, 2022 | 251 new projects were recieved in 2024, 57 projects obtained Decision of Minister. | NR | No | NR | The programme document of the ENERGov programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
30 | MF 2023-1 CZ 0-013 | NR | Energy efficiency and energy savings in new buildings for public sector (ENERGov Programme) | Priority | Scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | LOŠBATES, dobrovolný svazek obcí (voluntary association of municipalities); Střední pedagogická škola Boskovice, příspěvková organizace (Secondary Pedagogical School Boskovice, contributory organization) | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 468750000 | 375000000 | 150000000 | 50000000 | 117320 | 0 | 0 | NR | 0 | 577000 | 0 | 445280 | 0 | 0 | #DIV/0! | 1052.7084 | No | 27 projects obtained a Decision of Minister in 2024. | NR | No | NR | The programme document of the ENERGov programme will be developed on the basis of the scheme and subsequently published on the SEF CR website (https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/). The requirements for audit and control activities will be specified here in the same way as in the RES+, HEAT and ENERG ETS programmes (see above). | NR | NR
31 | MF 2023-2 CZ 0-002 | NR | Construction of OV VP4 media preheating | Priority | Project | Construction ongoing | NR | Třinecké železárny, a. s. | CZ08 Moravskoslezsko | 13592496.63 | 11233468.29 | 4648807.34 | 4648807.34 | 4648807.34 | 1616686.758 | 0 | NR | 0 | 173600 | 0 | 140771.79 | 0 | 0 | #DIV/0! | 96.557 | No | NR | 2025-04-01 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | NR | NR
32 | MF 2023-2 CZ 0-003 | NR | EGT-transition to low-emission heat and power generation – Stage 1. | Priority | Project | Tender ongoing | NR | Energotrans, a. s. | CZ02 Střední Čechy | 611085139 | 505029040 | 307762161 | 307762161 | 307762161 | 0 | 0 | NR | 0 | 9216440 | 0 | 5684230 | 0 | 0 | #DIV/0! | 107.5054 | Yes, 2022 | NR | 2028-12-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
33 | MF 2023-2 CZ 0-005 | NR | The Construction of a steam-gas cycle PPC2 at The UE Komořany | Priority | Project | Not started | NR | United Energy, a.s. | CZ04 Severozápad | 103233985 | 103064365 | 62399645 | 62399645 | 62399645 | 0 | 0 | NR | 0 | 2671000 | 0 | 1499910 | 0 | 0 | #DIV/0! | 68.8268 | No | NR | 2028-11-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
34 | MF 2023-2 CZ 0-006 | NR | Replacement of a coal block with a gas source - STAGE II | Priority | Project | Tender ongoing | NR | Elektrárny Opatovice a.s. | CZ05 Severovýchod | 94489667 | 78090634 | 47848099 | 47848099 | 47848099 | 0 | 0 | NR | 0 | 1766060 | 0 | 1351318 | 0 | 0 | #DIV/0! | 69.9241 | No | NR | 2027-04-05 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
35 | MF 2023-2 CZ 0-008 | NR | EVO Planá - Energie z odpadu Táborska / WtE Planá | Priority | Project | Not started | NR | C-Energy Planá s.r.o. | CZ03 Jihozápad | 108565145 | 89723261 | 58441401 | 58441401 | 58441401 | 0 | 0 | NR | 0 | 1450160 | 0 | 574000 | 0 | 0 | #DIV/0! | 189.1379 | Yes, 2022 | NR | 2027-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | NR | NR
36 | MF 2024-1 CZ 0-001 | MF 2024-2 CZ 0-011 | Scheme: Installation of photovoltaic power plants in households of the “RES+” Programme (New renewable energy sources) | Priority | Large-scale scheme | Construction ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Households in the Czech Republic, where no economic activity is performed. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 2768480000 | 2288000000 | 800000000 | 800000000 | 698609569.8729 | 698609569.8729 | 0 | NR | 1718094.7853 | 1093458.3 | 653842.3576 | 8435000 | 397.11 | 980.8 | 4234.1705 | 328.2134 | Yes, 2023 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
37 | MF 2024-1 CZ 0-002 | NR | Scheme: Aid for installation of photovoltaic power plants to address self-consumption of energy (in enterprises) of the “RES+” Programme (New renewable energy sources) | Priority | Large-scale scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Enterprises based in the Czech Republic whose aim is not to maximise the production of renewable energy for sale or distribution, but to address their own energy needs through energy produced from renewable sources. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 1730000000 | 1430000000 | 500000000 | 5000000 | 0 | 0 | 0 | NR | 0 | 0 | 0 | 9749000 | 0 | 1130 | #DIV/0! | 177.4541 | Yes, 2024 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the RES+ programme document (chapter 10.4.3, page 27, https://www.sfzp.cz/files/documents/storage/2021/05/20/1621500994_ModF_RES_EN.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
38 | MF 2024-1 CZ 0-003 | NR | Scheme: Modernisation of public transport – electric and H2 passenger trains priority investments of the Programme “TRANSGov” (Modernization of public transport) | Priority | Large-scale scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Public entities, organisations with property participation of the state and/or public entities, and public non-business entities together with business entities with public service obligation (PSO). | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 984441907 | 813588353 | 615085029 | 5000000 | 0 | 0 | 0 | NR | 0 | 849620 | 0 | 285429.9 | 0 | 0 | #DIV/0! | 3448.9796 | Yes, 2022, 2023 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the TRANSPORT programme document (chapter 9.4, page 11, https://www.sfzp.cz/files/documents/storage/2024/09/06/1725621203_ModF_TRANSPORT_09-2024.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
39 | MF 2024-1 CZ 0-004 | NR | Scheme: Modernisation of public transport – buses, trolley buses and tramways priority investments of the Programme “TRANSGov” (Modernization of public transport) | Priority | Large-scale scheme | Not started | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Public entities, organisations with property participation of the state and/or public entities, and public non-business entities together with business entities with public service obligation (PSO). | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 725180865 | 599323029 | 299661515 | 5000000 | 0 | 0 | 0 | NR | 0 | 2198230 | 0 | 706143.83 | 0 | 0 | #DIV/0! | 1026.9591 | Yes, 2023 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the TRANSPORT programme document (chapter 9.4, page 11, https://www.sfzp.cz/files/documents/storage/2024/09/06/1725621203_ModF_TRANSPORT_09-2024.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
40 | MF 2024-1 CZ 0-005 | NR | Modernisation of nitric acid production | Priority | Project | Construction ongoing | NR | BorsodChem MCHZ, s.r.o. | CZ08 Moravskoslezsko | 167585000 | 138500000 | 60211773 | 60211773 | 60211773 | 7431786.2974 | 0 | NR | 0 | 1274010 | 0 | 468652 | 0 | 0 | #DIV/0! | 357.5894 | Yes, 2021, 2022, 2023 | NR | 2026-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
41 | MF 2024-1 CZ 0-006 | NR | Reduction of CO2 emissions during heat production | Priority | Large-scale project | Tender ongoing | NR | Mondi Štětí a.s. | CZ04 Severozápad | 251661841 | 207984992 | 124526841 | 5000000 | 124526841 | 0 | 0 | NR | 0 | 8736150 | 0 | 3076387 | 0 | 264.7 | #DIV/0! | 81.8044 | Yes, 2023 | NR | 2030-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
42 | MF 2024-1 CZ 0-007 | NR | New Polymerization Plant (NPP) | Priority | Large-scale project | Tender ongoing | NR | Spolana s.r.o. | CZ02 Střední Čechy | 325792047 | 269249626 | 103126483 | 5000000 | 103126483 | 0 | 0 | NR | 0 | 575085 | 0 | 123450.4 | 0 | 0 | #DIV/0! | 2639.0522 | Yes, 2023 | NR | 2027-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
43 | MF 2024-1 CZ 0-010 | NR | ALFAGEN – Modernisation of the melting and casting technology | Priority | Large-scale project | Construction ongoing | NR | AL INVEST Břidličná, a.s. | CZ08 Moravskoslezsko | 208949595 | 172685616 | 79117830 | 5000000 | 79117830 | 0 | 0 | NR | 0 | 243822.33 | 0 | 50007.79 | 0 | 0 | #DIV/0! | 4178.3409 | Yes, 2023 | NR | 2027-06-30 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
44 | MF 2024-1 CZ 0-011 | NR | Decarbonisation of the Karviná CHP Plant – part: Multi-fuel Boiler with Combined Heat and Power Generation and Gas-fired CHP Installation with Combined Heat and Power Generation | Priority | Large-scale project | Tender ongoing | NR | Veolia Energie ČR, a.s. | CZ08 Moravskoslezsko | 384973532 | 318159945 | 204589717 | 5000000 | 204589717 | 0 | 0 | NR | 0 | 4555786.1111 | 0 | 1353000 | 0 | 58.3 | #DIV/0! | 284.5333 | Yes, 2023, 2024 | NR | 2027-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
45 | MF 2024-1 CZ 0-014 | NR | Modernisation of the Olomouc CHP Plant – Part: Multi-Fuel Boiler and Gas-fired CHP Unit | Priority | Large-scale project | Tender ongoing | NR | Veolia Energie ČR, a.s. | CZ07 Střední Morava | 203760897 | 168397436 | 102218068 | 5000000 | 102218068 | 0 | 0 | NR | 0 | 5872388.8889 | 0 | 760150 | 0 | 0 | #DIV/0! | 268.0535 | Yes, 2023, 2024 | NR | 2027-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
46 | MF 2024-1 CZ 0-019 | NR | CV_PM 45 MW EPR, Prunéřov | Priority | Large-scale project | Tender ongoing | NR | ČEZ Teplárenská, a. s. | CZ04 Severozápad | 141448741 | 116899786 | 72539137 | 5000000 | 72539137 | 0 | 0 | NR | 0 | 2697086.1111 | 0 | 1473780 | 0 | 0 | #DIV/0! | 95.9768 | Yes, 2024 | NR | 2027-11-30 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
47 | MF 2024-2 CZ 0-001 | NR | Renewal of the heat and power plant Teplárna | Priority | Project | Tender ongoing | NR | Plzeňská teplárenská, a.s. | CZ03 Jihozápad | 120059732 | 99222919 | 50430329 | 30430329 | 50430329 | 0 | 0 | NR | 0 | 4039880 | 0 | 2134200 | 0 | 0 | #DIV/0! | 56.2551 | Yes, 2023 | NR | 2028-05-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
48 | MF 2024-2 CZ 0-002 | NR | Strategy for a green city – ZEVO Vráto | Priority | Large-scale project | Tender ongoing | NR | ZEVO Vráto, a.s. | CZ03 Jihozápad | 379732412 | 313828440 | 186907236 | 5000000 | 186907238 | 0 | 0 | NR | 0 | 2255638.8889 | 0 | 896955 | 0 | 0 | #DIV/0! | 423.3573 | Yes, 2023, 2024 | NR | 2028-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
49 | MF 2024-2 CZ 0-003 | NR | WtE Opatovice | Priority | Large-scale project | Not started | NR | Elektrárny Opatovice, a.s. | CZ05 Severovýchod | 331306880 | 273807339 | 160832654 | 5000000 | 160832654 | 0 | 0 | NR | 0 | 6135936.3889 | 0 | 1508851.8 | 0 | 0 | #DIV/0! | 219.5755 | Yes, 2023, 2024 | NR | 2029-03-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
50 | MF 2024-2 CZ 0-004 | NR | Replacement of a coal block with a gas source - STAGE III | Priority | Project | Not started | NR | Elektrárny Opatovice a.s. | CZ05 Severovýchod | 124331915 | 102753649 | 62094215 | 62094215 | 62094215 | 0 | 0 | NR | 0 | 1959256.3333 | 0 | 1475781.3 | 0 | 0 | #DIV/0! | 84.2482 | Yes, 2023, 2024 | NR | 2028-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
51 | MF 2024-2 CZ 0-005 | NR | Renewal of the heat and power plant Energetika | Priority | Large-scale project | Not started | NR | Plzeňská teplárenská, a.s. | CZ03 Jihozápad | 180030497 | 148785535 | 76994254 | 5000000 | 76994254 | 0 | 0 | NR | 0 | 8614110 | 0 | 1963080 | 0 | 0 | #DIV/0! | 91.7082 | Yes, 2024 | NR | 2029-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
52 | MF 2024-2 CZ 0-006 | NR | Replacement of a coal block with a gas source - STAGE IV | Priority | Large-scale project | Not started | NR | Elektrárny Opatovice, a.s. | CZ05 Severovýchod | 156010296 | 128934129 | 78740424 | 5000000 | 78740424 | 0 | 0 | NR | 0 | 2049245.0556 | 0 | 1882333.5 | 0 | 0 | #DIV/0! | 82.8813 | Yes, 2023, 2024 | NR | 2029-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
53 | MF 2024-2 CZ 0-007 | NR | Electrolytic production of renewable hydrogen of the “GREENGAS” Programme | Priority | Scheme | Tender ongoing | The program document under the scheme of the same title is published on this site: https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/dokumenty/ The calls announced from all programs/schemes of the Modernization Fund implemented in the Czech Republic are presented on this site (where one can choose both the current calls and the closed calls under the specific programs): https://www.sfzp.cz/dotace-a-pujcky/modernizacni-fond/vyzvy/ | Enterprises, public entities and energy communities based in the Czech Republic. | The whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | 568673944 | 469978466 | 200000000 | 5000000 | 0 | 0 | 0 | NR | 0 | NA | 0 | 1604120 | 0 | 214 | #DIV/0! | 354.5084 | Yes, 2024 | NR | NR | No | NR | The audit and on-site inspections for this project are governed by the GREENGAS programme document (chapter 9.4, page 11, https://www.sfzp.cz/files/documents/storage/2024/09/12/1726144592_ModF_GREENGas_n%C3%A1vrh%20podm%C3%ADnek_09-2024.pdf). | Consulted during the meeting of the Platform for the ModFund on 6-12-2023 and approved. | NR
54 | MF 2024-2 CZ 0-008 | NR | New energy source NA7 | Priority | Large-scale project | Not started | NR | Lovochemie, a.s. | CZ04 Severozápad | 286414634 | 236706309 | 129531109 | 5000000 | 129531109 | 0 | 0 | NR | 0 | 1285697 | 0 | 860120 | 0 | 0 | #DIV/0! | 332.9938 | Yes, 2021, 2022, 2023, 2024 | NR | 2029-01-01 | No | No changes | The audit and on-site inspections for this project are governed by the ENERG ETS programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/09/21/1695282700_ModF_ENERG%20ETS_EN_09-2023.pdf). | Consulted during the meeting of the Platform for the ModFund on 18-6-2024 and approved. | NR
55 | MF 2024-2 CZ 0-010 | NR | Decarbonisation and Modernisation of the Ostrava Location | Priority | Large-scale project | Not started | NR | Veolia Energie ČR, a.s. | CZ08 Moravskoslezsko | 720659953 | 595586738 | 297793369 | 5000000 | 297793369 | 0 | 0 | NR | 0 | 4716130 | 0 | 2924370 | 0 | 0 | #DIV/0! | 246.4325 | No | NR | 2029-12-31 | No | No changes | The audit and on-site inspections for this project are governed by the HEAT programme document (chapter 9.4.3, page 17, https://www.sfzp.cz/files/documents/storage/2023/02/22/1677054553_ModF_HEAT_ENG_2022.pdf). | Consulted during the meeting of the Platform for the ModFund on 18-6-2024 and approved. | NR
Note on O3: RM od r. 2021 do konce 2023
Note on O6: kurz k 18.4.2024
Note on S6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W6: 7221100003 - FVE Impregnace Soběslav
Note on Y6: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y7: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y8: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y9: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y10: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y11: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y12: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y13: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y14: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y15: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y16: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y17: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y18: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y19: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y20: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y21: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y22: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y23: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y24: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y25: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y26: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y27: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y28: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y29: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y30: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y31: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y32: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y33: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y34: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y35: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y36: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y37: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y38: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y39: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y40: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S41: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U41: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W41: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y41: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y42: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y43: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y44: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y45: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y46: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y47: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y48: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y49: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y50: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y51: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y52: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y53: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y54: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y55: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y56: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y57: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y58: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y59: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on S60: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on U60: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on W60: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.
Note on Y60: According to SEF methodology, the project contributions are reported only after the project‘s successful completion. No project has been fully completed yet.

## Overview Planned Investment
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment/Název a reference investice | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) / | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investmen
1 | Individual investment: Transition to low-emission heat and power generation, stage 3. Energotrans, a.s. (ČEZ) | State Environmental Fund of the Czech Republic | CZ02 Střední Čechy | 1277788229 | The subject of the project is the replacement of the heat source in the thermal energy supply system with a change of the fuel base from coal to natural gas in combination with a high-efficiency CHP. | pending | 361336721 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
2 | Individual investment: UL_PPC 100 MWth (150 Mwe), Trmice | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 309404877 | The aim of the project UL_PPC 100 MWth (150 Mwe), Trmice is the construction of a steam-gas cycle (PPC) in the configuration of two combined cycle gas turbines (CCGT) incl. HRSG and one shared steam turbine with total thermal output to district heating system (DHS) of 100 MWth and electrical output 150 MWe. The new heat source will replace the heat from the existing coal-fired boilers K5, K6 supplied to the DHS as part of the phased renewal of the entire site. | pending | 182457060 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
3 | Individual investment: Heating plant T600 | State Environmental Fund of the Czech Republic | CZ04 Severozápad | 1022262414 | The existing lignite heating plant was put into operation in the 1960s and underwent a major renovation in the 1990s. Due to the poor technical condition of the facility and the need to address the stricter BREF LCP emission limits set by current and expected legislation after 2025, it was decided to shut down the heating plant; replacement with a new natural gas-based cogeneration source must take place by the end of 2027 at the latest. | pending | 481825214 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
4 | Individual investment: Optimisation of the energy management of the KRONOSPAN Jihlava | State Environmental Fund of the Czech Republic | CZ06 Jihovýchod | 302250839 | KRONOSPAN is producing agglomerated wood-based boards for furniture and for construction. The main input material is recycled wood, wood waste and damaged wood (e.g. by bark beetle) which needs to be processed prior the production. This wood scrap from such processing will be used to produce the maximum possible amount achievable production of electricity. The new power unit will consist of a steam boiler with grate combusting wood-based biomass with a fuel input of 100 MW and a highly efficient cogeneration with a turbine with a nominal output of 19 MWe. All generated electricity will be fully consumed within the production plant. | pending | 136965189 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
5 | Individual investment: Modernization and decarbonization of steel production | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 990074090.05 | The proposed solution consists in changing the technology of steel production in Třinecké železárny with the aim of significantly reducing the emission footprint of production. The new technology consists in the production of steel in electric arc furnaces mainly from steel scrap, while the recyclability of steel is fully utilized and the main energy input is electrical energy (instead of the current coke and pulverized coal as part of "ore technology"). In addition to scrap, ore input can also be used in the production of steel in electric arc furnaces, namely so-called directly reduced iron, which is produced by reducing ore pellets using natural gas, carbon (or hydrogen). | pending | 475266347.18 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2023-12-06 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
6 | Individual investment: Modernization of the KJT (long rolled products) line | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 208668541.4 | The subject of the project is a significant part of the investment generating energy savings, namely the modernization of the rolling line. There will be an installation of new technological equipment (rolling stands, shears, flatbeds, drives and cooling beds) for hot bar rolling in the existing premises of the KJT Rolling Mill, which will replace the existing equipment and thus enable an increase in production quality including a reduction in energy consumption. | pending | 67949364.8 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
7 | Individual investment: Modernization of electrostatic precipitators at Agglomeration 2 | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 37414775.42 | The subject of the submitted project is the modernization of the electrostatic precipitators at Agglomeration 2, which will lead to energy savings. The project will include the replacement of electrostatic precipitators No. 3 and No. 4, electrical wiring, construction solutions, MAR, technological structures including the collector pipeline of the sintering belts, the inlet pipeline of the electrostatic precipitator, and construction modifications. | pending | 16455897.8 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
8 | Individual investment: Modernization of billet grinder extraction | State Environmental Fund of the Czech Republic | CZ08 Moravskoslezsko | 4661355.6 | The aim of the project is to replace the equipment for secondary dust separation and grinding dust removal (extraction) including drives. The subject of the modernization will also be the modernization of the exhaust pipe from the point of connection to the grinder to the new filter. The complete replacement of the filter equipment for the grinder exhaust, including the drives, will result in a reduction in the total final energy consumption by at least 20.46%, which is based on the design of the existing drives, their age, efficiency, wear and tear and by reducing the installed power of the fan drives, together with the optimal dimensioning of the newly designed filter exhaust for the grinders. | pending | 1522078.76 | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
9 | Scheme: Freight transport (TRANSCom programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | TBD | Measures to increase energy efficiency in freight commercial transport | pending | TBD | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.
10 | Scheme: Energy communities (KOMUNERG programme) | State Environmental Fund of the Czech Republic | Location of the investment activity is the whole Czech Republic, i.e.: CZ01 Praha, CZ02 Střední Čechy, CZ03 Jihozápad, CZ04 Severozápad, CZ05 Severovýchod, CZ06 Jihovýchod, CZ07 Střední Morava, CZ08 Moravskoslezsko. | TBD | Aid for establishment of energy communities | pending | TBD | Contribution especially to: • National Energy and Climate Plan; • State Energy Policy; • The Climate Protection Policy; • National emission reduction programme. Other national energy and climate action plans are also benefitted due to the focus of the project on change of solid fossil fuel base to climate more friendly fuels and enhancing energy efficiency. | No | 2Q/2024 | Stakeholder meetings within the Modernisation Fund Platform including entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). It meets at least twice a year. | Entities whose competence includes areas supported by the Modernisation Fund (representatives of stakeholders from state administration bodies, professional associations, NGO´s, the professional public and other partners). | NR | Stakeholder consultation on the draft of this project resulted in a consensus view with the intention to bring the project to the closest possible meeting of the Modernisation Fund Investment Committee.

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia