## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: a) Column N refers to the Modernisation Fund support that EIB disbursed to the beneficiery MS by the cut-off date. b) Column Y (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column U (Greenhouse gas emissions saved in tCO2 - by 31 December of the year preceding report submission). The calculation formula should be shown in the cells. c) Column Z (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column V (Greenhouse gas emissions saved in tCO2 expected cumulative amount by end of the investment lifetime). The calculation formula should be shown in the cells.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2024 | Latvia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2023-1 LV 0-001 | - | Energy efficiency in transport sector - support for introduction of electric vehicles and corresponding charging infrastructure | Priority | Scheme | Tender ongoing | Regulations of the Cabinet of Ministers No 701 (05.11.2024.): https://likumi.lv/ta/id/356200 | - | - | 6050000 | 5000000 | 5000000 | 0 | 0 | 0 | - | - | - | 7680 | - | 8320 | - | 0.125 | - | 727.1635 | Yes, mentioned as one of the priority investment areas in the submitted annual report of the year 2022. | In November 2024, an open project tender "Energy efficiency in transport sector - support for introduction of electric vehicles and corresponding charging infrastructure" with the total funding 5 MEUR was announced. The submission of project applications was closed in February 2025. Within the scheme, support for the purchase of electric vehicles and creation of corresponding charging infrastructure may be granted to municipalities, state direct administration institutions and companies which meet the requirements of the Cabinet Regulations. The evaluation of project applications was completed in April 2025, after which contracts with project implementers are scheduled to be concluded. Considering that not all available funding was allocated in the first round of the call for proposals, the announcement of the next round is planned in May, 2025. | - | Not identified. | - | - | - | -
2 | MF 2024-1 LV 0-001 | - | Use of renewable energy sources in multiapartment buildings, public buildings, and energy communities | Priority | Scheme | Not started | Draft Regulations of the Cabinet of Ministers: https://tapportals.mk.gov.lv/legal_acts/531a294f-c9d0-43a6-b719-96c41f88c877 | - | - | 32428000 | 26800000 | 26800000 | 0 | 0 | 0 | - | - | - | - | - | 125764 | - | 20.5 | - | 257.848 | Yes, mentioned as one of the priority investment areas in the submitted annual report of the year 2023. | In the end of 2024, the development of an open project tender "Use of renewable energy sources in multi-apartment buildings, public buildings, and energy communities" with the total funding of 26,8 MEUR started. Requirements and conditions for project applicants will be layed down by the Cabinet Regulations. The scheme is planned to be approved in the 2nd quarter of 2025. Public consultation took place in April, 2025, in which some comments were received. After that interministerial discussions will start. | - | - | - | - | - | -
3
4
5
6
7
8
9
10
11
XX

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Support for an increased capacity of the Latvia’s electricity grid (MF 2025-1 LV 0-001) | Managing authority - Ministry of Climate and Energy of the Republic of Latvia, project proponent - JSC "Sadales tīkls" | Latvia | 48400000 | Confirmed as priority investment by the EIB on March 17, 2025. The objective of the investment is to increase the capacity of the national electricity grid by building additional 110kV connecting line (to increase the capacity of an existing Salacgrīva electricity substation) and by building two new substations. | Not applicable | 40000000 | National Energy and Climate Plan 2021-2030 - 3.4.2.2. measure "Implementation of internal energy infrastructure modernisation projects in accordance with the 10-year development plans of TSO and DSOs" | - | 2022-2023 | Initial consultation of priority investment areas was taken when the Regulation of the Cabinet of Ministers “Rules of operation of the Modernisation Fund and multiannual operational programme” was developed in 2022 and 2023 in which priority investment areas for the period until 2027 were set. The overall priority investment areas are agreed with sectoral ministries and social partners. Public consultation was organized in 2022 as well. The investment is implemented within the framework of a priority investment area "Promotion of energy efficiency and use of renewable energy for enterprises in energy production, distribution and transmission processes". Consultation where more detailed terms regarding the regulation of the project tender for the respective investment will be provided when the regulation will be developed (in 2025). Within the development of the regulation of the project tender, public consultation will also be provided, as well as consultation with sectoral ministries and social partners. | General public, sectoral ministries and social partners | 2 comments from social partners; no comments from general public. Separate consultation with sectoral ministries, social partners and general public will be provided for the respective draft Regulation of the Cabinet of Ministers. | Comments on the general priority investment area "Promotion of energy efficiency and use of renewable energy for enterprises in energy production, distribution and transmission processes" - proposals for improving the wording of the regulation, a proposal to implement the relevant measures in accordance with the sustainable energy and climate plans of municipalities and companies.
2 | Promotion of energy efficiency and use of renewable energy for enterprises in energy production, distribution and transmission processes | Ministry of Climate and Energy of the Republic of Latvia | Latvia | 58322000 | Priority scheme per the ETS directive. Promotion of energy efficiency improvements and the use of renewable energy resources for enterprises in energy generation, transmission, distribution and production processes, modernisation or expansion of electricity infrastructure and the introduction of smart technologies and digital solutions, and the related measures that comply with circular economy principles. Investment proposal is expected to be submitted for second disbursement cycle of 2025. The planned activities are intended to promote energy security and electrification, including underground cabling. | Pending | 48200000 | National Energy and Climate Plan 2021-2030 - 3.4.2.2. measure "Implementation of internal energy infrastructure modernisation projects in accordance with the 10-year development plans of TSO and DSOs", 3.4.2.10. measure "Move energy transmission and distribution infrastructure underground". Several measures related to the electrification are alse defined in the NECP and will be clarified in the relevant investment proposal. | - | 2022-2023 | Initial consultation of priority investment areas was taken when the Regulation of the Cabinet of Ministers “Rules of operation of the Modernisation Fund and multiannual operational programme” was developed in 2022 and 2023 in which priority investment areas for the period until 2027 were set. The overall priority investment areas are agreed with sectoral ministries and social partners. Public consultation was organized in 2022 as well. Consultation where more detailed terms regarding the regulation of the project tender for the respective investment will be provided when the regulation will be developed (in 2026). Within the development of the regulation of the project tender, public consultation will also be provided, as well as consultation with sectoral ministries and social partners. | General public, sectoral ministries and social partners | 2 comments from social partners; no comments from general public. Separate consultation with sectoral ministries, social partners and general public will be provided for the respective draft Regulation of the Cabinet of Ministers. | Comments on the general priority investment area "Promotion of energy efficiency and use of renewable energy for enterprises in energy production, distribution and transmission processes" - proposals for improving the wording of the regulation, a proposal to implement the relevant measures in accordance with the sustainable energy and climate plans of municipalities and companies.
3
4
5
6
7
8
9
10
11
XX

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia