## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: a) Column N refers to the Modernisation Fund support that EIB disbursed to the beneficiery MS by the cut-off date. b) Column Y (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column U (Greenhouse gas emissions saved in tCO2 - by 31 December of the year preceding report submission). The calculation formula should be shown in the cells. c) Column Z (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column V (Greenhouse gas emissions saved in tCO2 expected cumulative amount by end of the investment lifetime). The calculation formula should be shown in the cells.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2025 | Slovenia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | Ror investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2024-2 SI-001 | N/A | Scheme RES (Part A): Production of electricity from renewable energy sources – solar, wind and hydro | Priority investment | Scheme | Tender ongoing | ZSROVE: https://www.pisrs.si/Pis.web/pregledPredpisa?id=ZAKO8206 ZUNPEOVE: https://www.pisrs.si/Pis.web/pregledPredpisa?id=ZAKO8966 | Targeted beneficiaries are some of the largest energy producing public companies in Slovenia, owned by the State, whose aim is to decarbonise the energy sector by constructing additional capacities. | Due to the ongoing public invitation, there are no final locations yet. Indicative example: Šaleška dolina (SAŠA region), undergoing coal phase-out and just transition | 272563813.05 | 223429934.79 | 84086045.74 | 29522515.32 | 0.00 | 0.00 | No amounts have been recovered to date | Not applicable – the investment is classified as a priority investment. | 0 | 5776700 | 0 tCO₂ | 2.863.542,50 tCO₂ | 0 MW | 205.25 | 0 EUR/tCO₂ | 95.1841 | Yes, 2024 | Public call for project proposals launched (September 2023) Draft investment overview prepared and public consultation held (April 2024) Indicative list of investment proposals compiled based on call results No objections raised during stakeholder consultation Cost estimates refined based on updated project documentation (August 2024) Public invitation for the selection of projects published (July 2025) | Not applicable – the investment is a scheme, not an individual project. | No identified or expected delays in implementation. | Not applicable – the investment is a scheme, not an individual project. | No audits have been undertaken yet at national level in accordance with Article 16(4) of Implementing Regulation (EU) 2020/1001, as the scheme has not yet commenced. Audit activities will be planned and reported following the first disbursement and implementation phase. | Not applicable, as this is not a large-scale scheme. | Not applicable - investment was approved before 1 January 2025. However, projects within the scheme will have to self-evaluate their compliance with DNSH principle, which will be checked by the Ministry of the Environment, Climate and Energy, and sign a confirmation of compliance with DNSH.
2
3
4
5
6
7
8
9
10
11
XX

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Scheme EE (Part A): Modernisation and development of the electricity transmission and distribution network | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia - multiple locations | 384674883.67 | Scheme EE covers modernisation of Slovenian electricity transmission and distribution network, which consists of different related investments in low-voltage (LV), medium-voltage (MV) and high-voltage (HV) grids, implemented by national TSOs/DSOs, such as: automation, digitalisation and development for the electricity transmission and distribution network, replacement and reconstruction of transformer substations, extension and reconstruction of switchgears, telecontrol system integration, construction and replacement of cable lines etc. Investment supported by Scheme EE will ensure an autonomous, resilient and reliable network that will automatically be able to adapt to the current market situation, making it possible to connect more renewable energy production sources, recharging infrastructure and to electrify heating by connecting more heat pumps. | Completed ("natural monopoly" in line with point 375 of Commission Guidelines on State aid for climate, environmental protection and energy 2022 (OJ C 80, 18.2.2022, pp. 1–89). | Modernisation Fund: €154.279.868,65 (1st disbursement in 2025: €30.000.000,00, 2nd disbursement in 2026: €30.000.000,00, 3rd disbursement in 2027: €30.000.000,00, 4th disbursement in 2028: €30.000.000,00, 5th disbursement in 2029: €34.279.868,65) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Energy Security Dimension and Internal Energy Market Dimension, namely: a) Energy Security - ensuring a reliable and competitive energy supply, maintaining a high level of electricity connection with neighbouring countries; ensuring an adequate level of security of electricity supply; increasing distribution network resistance to disruption (by increasing the proportion of underground MV network to at least 50 %); further development of system services and active role of consumers; development of energy storage technologies, infrastructure and services; b) Internal Energy Market - ensuring additional financial, human and technical resources to accelerate integrated development and management of the electricity distribution network for increased capacity, resilience to disruption, future development potential, connectivity and adaptability (to enable the exploitation of the flexibility of resources and loads, the integration of heat pumps, the accelerated deployment of e-mobility, the integration of renewable electricity generation and storage devices). | N/R | Please see annex (Annex_1_public_consultation) for all responses to this part of the overview.
2 | Scheme RES (Part A): Production of electricity from renewable energy sources - solar, wind and hydro | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia - multiple locations | 285963808.07 | Scheme RES covers construction, reconstruction of electricity generation installation from renewable energy sources, including energy storage capacities, provided it is a part of the same investment. The scheme focuses on generation of electricity from renewable sources, such as solar, wind and hydro sources. | Completed (Article 41 of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €89.308.469,24 (1st disbursement in 2025: €45.000.000,00, 2nd disbursement in 2026: €44.308.469,24) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension, namely: effective placement of RES production capacities in space for accelerated use of RES; further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport, general consumption, agriculture, waste management, industry (non-ETS), energy (non-ETS)); achieving at least a 27% share of RES in energy end-use by 2030; decarbonisation of electricity production (at least by -30 % by 2030) etc. | N/R
3 | Scheme ZERO-EM (Part A): Energy efficient and clean transport - the path to zero-emission transport | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia | 169373570.32 | Scheme ZERO-EM covers investments in energy efficient and clean transport, aiming to assure zero-emission transport, e.g. by using alternative fuels, especially in public transport. The scheme will support investments, such as: a) modernisation of the Slovenian rolling stock for conducting public passenger transport in Slovenia and cross-border countries; b) construction of recharging infrastructure and electrification of the Port of Koper area with the purpose of electricity supply to ships from the shore and use of electricity as a clean propulsion alternative for cargo and passenger ships; c) deployment of publicly accessible alternative fuels infrastructure, such as charging pools, d) modernisation of information and communication technologies supporting integrated public passenger transport. Modernisation of rolling stock for public passenger transport Shore-side electricity supply to ships in the Port of Koper | Completed (Article 36a, 36b and 56b of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €75.713.793,60 (1st disbursement in 2024: €34.281.300,00, 2nd disbursement in 2027 or later: €41.432.493,60) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension and Energy Efficiency Dimension, namely: a) Decarbonisation - further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport); achieving at least a 27% share of RES in energy end-use by 2030 (with at least a 21 % share in transport); b) Energy Efficiency - improving energy and material efficiency in all sectors (by reducing consumption of energy and other natural resources); improving energy efficiency by at least 35% by 2030 (compared to the 2007 baseline scenario); faster implementation of programmes for informing, raising awareness and training of different target groups on the benefits and practical aspects of the development and use of energy efficiency technologies and the use of RES. | N/R
4 | Scheme EE (Part B): Modernisation and development of the electricity transmission and distribution network | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia - multiple locations | 170292622.02 | Scheme EE covers modernisation of Slovenian electricity transmission and distribution network, which consists of different related investments in low-voltage (LV), medium-voltage (MV) and high-voltage (HV) grids, implemented by national TSOs/DSOs, such as: automation, digitalisation and development for the electricity transmission and distribution network, replacement and reconstruction of transformer substations, extension and reconstruction of switchgears, telecontrol system integration, construction and replacement of cable lines etc. Investment supported by Scheme EE will ensure an autonomous, resilient and reliable network that will automatically be able to adapt to the current market situation, making it possible to connect more renewable energy production sources, recharging infrastructure and to electrify heating by connecting more heat pumps. | Completed ("natural monopoly" in line with point 375 of Commission Guidelines on State aid for climate, environmental protection and energy 2022 (OJ C 80, 18.2.2022, pp. 1–89). | Modernisation Fund: €68.812.809,88 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Energy Security Dimension and Internal Energy Market Dimension, namely: a) Energy Security - ensuring a reliable and competitive energy supply, maintaining a high level of electricity connection with neighbouring countries; ensuring an adequate level of security of electricity supply; increasing distribution network resistance to disruption (by increasing the proportion of underground MV network to at least 50 %); further development of system services and active role of consumers; development of energy storage technologies, infrastructure and services; b) Internal Energy Market - ensuring additional financial, human and technical resources to accelerate integrated development and management of the electricity distribution network for increased capacity, resilience to disruption, future development potential, connectivity and adaptability (to enable the exploitation of the flexibility of resources and loads, the integration of heat pumps, the accelerated deployment of e-mobility, the integration of renewable electricity generation and storage devices). | N/R
5 | Scheme RES (Part B): Production of electricity from renewable energy sources - solar, wind and hydro | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia - multiple locations | 374822489.77 | Scheme RES covers construction, reconstruction of electricity generation installation from renewable energy sources, including energy storage capacities, provided it is a part of the same investment. The scheme focuses on generation of electricity from renewable sources, such as solar, wind and hydro sources. | Completed (Article 41 of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €150.651.341,33 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension, namely: effective placement of RES production capacities in space for accelerated use of RES; further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport, general consumption, agriculture, waste management, industry (non-ETS), energy (non-ETS)); achieving at least a 27% share of RES in energy end-use by 2030; decarbonisation of electricity production (at least by -30 % by 2030) etc. | N/R
6 | Scheme ZERO-EM (Part B): Energy efficient and clean transport - the path to zero-emission transport | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia | 240518569.34 | Scheme ZERO-EM covers investments in energy efficient and clean transport, aiming to assure zero-emission transport, e.g. by using alternative fuels, especially in public transport. The scheme will support investments, such as: a) modernisation of the Slovenian rolling stock for conducting public passenger transport in Slovenia and cross-border countries; b) construction of recharging infrastructure and electrification of the Port of Koper area with the purpose of electricity supply to ships from the shore and use of electricity as a clean propulsion alternative for cargo and passenger ships; c) deployment of publicly accessible alternative fuels infrastructure, such as charging pools, d) modernisation of information and communication technologies supporting integrated public passenger transport. Modernisation of rolling stock for public passenger transport Shore-side electricity supply to ships in the Port of Koper | Completed (Article 36a, 36b and 56b of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €145.914.647,00 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension and Energy Efficiency Dimension, namely: a) Decarbonisation - further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport); achieving at least a 27% share of RES in energy end-use by 2030 (with at least a 21 % share in transport); b) Energy Efficiency - improving energy and material efficiency in all sectors (by reducing consumption of energy and other natural resources); improving energy efficiency by at least 35% by 2030 (compared to the 2007 baseline scenario); faster implementation of programmes for informing, raising awareness and training of different target groups on the benefits and practical aspects of the development and use of energy efficiency technologies and the use of RES. | N/R
7 | Scheme H2: Development of production capacities for renewable hydrogen | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia - multiple locations | 267048505.9 | Scheme H2 covers investments in construction of production capacities of renewable hydrogen, including dedicated infrastructure for the transmission or distribution of renewable hydrogen, as well as storage facilities for renewable hydrogen. | Completed (Article 41 of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €161.144.357,61 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension and Internal Energy Market Dimension, namely: a) Decarbonisation - further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport, general consumption, agriculture, waste management, industry (non-ETS), energy (non-ETS)); achieving at least a 27% share of RES in energy end-use by 2030 (with at least 30 % of renewables in industry and a 43 % share of RES in the production of electricity); decarbonisation of electricity production (at least by -30 % by 2030); gradual decarbonisation of energy-intensive industries by restructuring production processes with the introduction of green technologies etc.; b) Internal Energy Market Dimension - ensuring further development of the pipeline system in line with gas flows and system capacity, including new sources of renewable gas; preparing a regulatory and supportive environment for alternative renewable gas sources in the natural gas network (along with determining the maximum permissible fraction of hydrogen in the natural gas network); supporting the implementation of pilot projects for the production of synthetic methane and hydrogen (an indicative target of 10% renewable methane or hydrogen in the transmission and distribution network by 2030) etc.. | N/R
8 | Scheme W2E: Development of Waste-to-Energy power plants | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia (Ljubljana, Maribor, Celje) | 290429000 | Scheme W2E covers investments in construction, reconstruction of waste management facilities generating energy from waste (Waste-to-Energy power plants). | Pending (presumably a notification of an "ad hoc aid" to the EC, based on Commission Guidelines on State aid for climate, environmental protection and energy 2022 (OJ C 80, 18.2.2022, pp. 1–89)). | Modernisation Fund: €244.851.842,50 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension and Research, Innovation and Competitiveness Dimension, namely: a) Decarbonisation - further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in waste management); achieving at least a 27% share of RES in energy end-use by 2030 (with at least 30 % of renewables in industry); gradual decarbonisation of energy-intensive industries by restructuring production processes with the introduction of green technologies etc.; b) Research, Innovation and Competitiveness Dimension - implementation of targeted R&D programmes and demonstration projects to reach a climate-neutral society based on the direct interest of the economy or the public sector, and fulfilling national development goals, in particular in the areas energy efficiency, the circular economy and green energy technologies. | N/R
9 | Scheme BIO: Development of production capacities for biomass fuels | Ministry of the Environment, Climate and Energy (Ministrstvo za okolje, podnebje in energijo - MOPE) | Slovenia (Ljubljana) | 2300000 | Scheme BIO covers investments in production and storage of biofuels, bioliquids, biogas (including biomethane) and biomass fuels, in compliance with State Aid rules. The storage component shall obtain at least 75 % of its fuel content from directly connected biofuels, bioliquids, biogas (including biomethane) and biomass fuels production installations. | Completed (Article 41 of the General Block Exemption Regulation - Commission Regulation (EU) 2023/1315 of 23 June 2023 amending Regulation (EU) No 651/2014) | Modernisation Fund: €1.073.100,00 (if relevant, disbursement plan will be done at a later stage) | The scheme complies with Slovenian NECP 2020-2030, in particular regarding the national objectives, targets, policies and measures within the Decarbonisation Dimension and Internal Energy Market Dimension, namely: a) Decarbonisation - further reducing GHG emissions by 2030 (at least 20% compared to 2005), while achieving sectoral GHG reducement objectives (in transport, general consumption, agriculture, waste management, industry (non-ETS), energy (non-ETS)); achieving at least a 27% share of RES in energy end-use by 2030 (with at least 21 % share in transport, of which at least 11 % share of biofuels, and at least 41 % share in the heaitng and cooling sector); gradual decarbonisation of energy-intensive industries by restructuring production processes with the introduction of green technologies etc.; b) Internal Energy Market Dimension - ensuring further development of the pipeline system in line with gas flows and system capacity, including new sources of renewable and waste gas; preparing a regulatory and supportive environment for alternative renewable gas sources in the natural gas network; supporting the implementation of pilot projects for the production of synthetic methane and hydrogen (an indicative target of 10% renewable methane or hydrogen in the transmission and distribution network by 2030) etc.. | N/R
10
11
12
XX

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia