## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: a) Column N refers to the Modernisation Fund support that EIB disbursed to the beneficiery MS by the cut-off date. b) Column Y (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column U (Greenhouse gas emissions saved in tCO2 - by 31 December of the year preceding report submission). The calculation formula should be shown in the cells. c) Column Z (Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime) should be calculated as Column K (Total investment costs/total volume of the scheme/project with VAT in EUR) divided by Column V (Greenhouse gas emissions saved in tCO2 expected cumulative amount by end of the investment lifetime). The calculation formula should be shown in the cells.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2024 | Slovakia | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | For investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-2 SK 0-001 | Discontinued investment | State Aid Scheme to support the production of electricity from renewable energy sources from the Modernization Fund | Priority | Large-scale scheme |  | https://www.minzp.sk/files/oblasti/politika-zmeny-klimy/ets/schema-st-pomoci-mof_mhsr-eng_f.pdf | - | - | 499999200 | 416666000 | 250000000 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | Yes, 2021, 2022. | -
2 | MF 2021-2 SK 0-002 | 1. MF 2022-1 SK 0-003 2. MF 2023-2 SK 0-001 | State Aid Scheme to support the investments to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund: high-efficiency cogenerations | Priority | Large-scale scheme | Construction ongoing | https://obchodnyvestnik.justice.gov.sk/Handlers/StiahnutPrilohu.ashx?IdPriloha=445982&csrt=9045177587791257847 | see the sheet "Beneficiairies" | Bratislava, Zvolen, Martin, Handlová, Turčianske Teplice | 715200000 | 596000000 | 350000000 | 85000000 | 42432918.48 | 136978.65 | 0 | n/a | 0 | 14400000 | 0 | 7620000 | 0 | 50 | 0 | 93.8583 | Yes, 2021, 2022, 2023. | The second call under this investment proposal was launched on July 7, 2024 it and was closed on October 16, 2024. More than 40 applications were received with the requested amount approx. 350 mil. eur. The applications assessed as recommended after the external expert check are waiting for the approval at the national level. | n/a | n/a | n/a | The Implementing Body (Environmental Fund - EF) carries out the control of the provided funds in accordance with the contractual terms and conditions, which form an integral part of each contract between the EF and the beneficiary. These are specified in Chapter Four, “Project Control,” Article 11 of the Contractual Terms and Conditions (page 22): https://envirofond.sk/wp-content/uploads/2025/06/Vseobecne-zmluvne-podmienky-pre-poskytnutie-podpory-z-Environemntalneho-fondu-formou-dotacie-z-prostriedkov-Modernizacneho-fondu.pdf . |  | n/a
3 | MF 2021-2 SK 0-003 | 1. MF 2022-1 SK 0-002 2. MF 2023-2 SK 0-002 | State aid scheme to support the investments to modernise energy systems, including energy storage and energy efficiency improvement from the Modernisation Fund – DHC | Priority | Large-scale scheme | Construction ongoing | https://obchodnyvestnik.justice.gov.sk/Handlers/StiahnutPrilohu.ashx?IdPriloha=445982&csrt=9045177587791257847 | see the sheet "Beneficiairies" | Komárno, Humenné, Nitra, Topoľčany | 918000000 | 765000000 | 650000000 | 124500000 | 107770678.61 | 24736197.91 | 0 | n/a | 749.3 | 3700000 | 25.388 | 800000 | 0 | 0 | 45192.5571 | 1147.5 | Yes, 2021, 2022, 2023. | The second call was launched on July 7, 2024 it and was closed on October 16, 2024. More than 40 applications were received with the requested amount approx. 350 mil. eur. After external expert check are waiting for the approval at the national level. | n/a | n/a | n/a | The Implementing Body (Environmental Fund - EF) carries out the control of the provided funds in accordance with the contractual terms and conditions, which form an integral part of each contract between the EF and the beneficiary. These are specified in Chapter Four, “Project Control,” Article 11 of the Contractual Terms and Conditions (page 22): https://envirofond.sk/wp-content/uploads/2025/06/Vseobecne-zmluvne-podmienky-pre-poskytnutie-podpory-z-Environemntalneho-fondu-formou-dotacie-z-prostriedkov-Modernizacneho-fondu.pdf . |  | n/a
4 | MF 2022-2 SK 0-002 | - | Scheme State aid scheme for the decarbonisation of industry from the Modernization fund | Priority | Large-scale scheme | Construction ongoing | https://obchodnyvestnik.justice.gov.sk/Handlers/StiahnutPrilohu.ashx?IdPriloha=413728&csrt=16445548320164838832 | https://www.minzp.sk/files/zoznam-schvalenych-prijimatelov-mof.pdf | Bratislava, Rohožník, Lednické Rovne | 900000000 | 750000000 | 750000000 | 350000000 | 140 761 435,94 | 113512 | 0 | n/a | 0 | 78000000 | 0 | 3000000 | 0 | 57.7 | 0 | 300 | Yes: 2021, 2022, 2023. | The Ministry of Environment of the Slovak Republic is internally assessing the preparation and setting of conditions for the second call. | n/a | Public consultations with potential applicants will take place July, 8 2025, which will also determine the planning of further steps and the launch of the second call. | n/a | The control is carried out in accordance with the Financial Control Act (Act No. 357/2015 Coll. on Financial Control and Audit and on Amendments to Certain Acts, as amended), through basic financial control, administrative financial control, and on-site financial control. The audit of a project is conducted as a governmental audit, also in accordance with the Financial Control Act. Details of the control and audit procedures are outlined in the General Terms and Conditions, which form an annex to each contract between the Implementing Authority and the Beneficiary. |  | n/a
5 | MF 2024-1 SK 0-001 | MF 2024-2 SK 0-001 | Scheme of state aid from the Modernization Fund resources to support investments for the production of energy from renewable energy sources, the production of renewable hydrogen and highly efficient cogeneration | Priority | Large-scale scheme | Tender ongoing | https://obchodnyvestnik.justice.gov.sk/Handlers/StiahnutPrilohu.ashx?IdPriloha=448848&csrt=9045177587791257847 | assessment of applications ongoing | assessment of applications ongoing | 933600000 | 778000000 | 350000000 | 50000000 | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 13460395.4 | 0 | 1031.1 | 0 | 69.359 | Yes: 2023. | The first call was launched on January, 15 2025 and was closed on April, 15 2025. The next step is the formal check of the aplications received. | n/a | n/a | n/a | The Implementing Body (Environmental Fund - EF) carries out the control of the provided funds in accordance with the contractual terms and conditions, which form an integral part of each contract between the EF and the beneficiary. These are specified in Chapter Four, “Project Control,” Article 11 of the Contractual Terms and Conditions (page 22): https://envirofond.sk/wp-content/uploads/2025/06/Vseobecne-zmluvne-podmienky-pre-poskytnutie-podpory-z-Environemntalneho-fondu-formou-dotacie-z-prostriedkov-Modernizacneho-fondu.pdf . | The Ministry prepared the first draft of the state aid scheme "State aid scheme from the resources of the Modernisation Fund to support investments in the production of heat and/or cold from renewable energy sources, the production of renewable hydrogen and to support highly efficient combined production" which was presented in summer 2023 during the consultations with potential and eligible subjects/beneficiaries of support under this Scheme. Received comments and amending proposals from the mentioned subjects were internally assessed, incorporated after consideration or discussed in more detail in online meetings. In autumn 2023, the Ministry invited potential beneficiaries to send their investment proposals eligible for support under this Scheme. About 30 projects were received in the amount of total investment costs of approx. 750 million EUR.
6 | MF 2024-2 SK 0-002 | - | Investment support of increasing the energy efficiency of existing public buildings | Priority | Large-scale scheme | Tender ongoing | https://envirofond.sk/wp-content/uploads/2025/04/Vyzva-MOF-4.2025-konsolidovane-znenie-v-zmysle-usmernenia.pdf | assessment of applications ongoing | assessment of applications ongoing | 492000000 | 400000000 | 380000000 | 10000000 | 0 | 0 | 0 | n/a | 0 | 833333.3 | 0 | 168333.3 | 0 | Real data will only become available during the implementation phase, after the completion of individual projects. | 0 | 2922.7729 | Yes: 2023. | The first call was launched on February, 28 2025 and will be open till April, 30 2025. | n/a | n/a | n/a | The Implementing Body (Environmental Fund - EF) carries out the control of the provided funds in accordance with the contractual terms and conditions, which form an integral part of each contract between the EF and the beneficiary. These are specified in Chapter Four, “Project Control,” Article 11 of the Contractual Terms and Conditions (page 22): https://envirofond.sk/wp-content/uploads/2025/06/Vseobecne-zmluvne-podmienky-pre-poskytnutie-podpory-z-Environemntalneho-fondu-formou-dotacie-z-prostriedkov-Modernizacneho-fondu.pdf . | Last year, the Ministry of the Environment and the Environmental Fund identified the need to follow up on the support for "Increasing the energy efficiency of existing public buildings, including insulation", which has been supported for several years from auctioning revenues in accordance with EU (directive 2003/87/ES) and national legislation. In summer 2023, a meeting of a working group consisting of representatives (relevant ministries, the Slovak Innovation and Energy Agency, the Slovak Government Office, etc.) was held to ensure mutual coordination of the actual support for the building sector. The planned measure was presented and discussed in May 2024 at a meeting with the Association of Towns and Municipalities of Slovakia, where representatives of municipalities showed a continuing interest in submitting applications for support for public buildings. Subsequently, in June 2024, meetings were held with the Ministry of Transport of the Slovak Republic and with the Slovak Innovation and Energy Agency (Structural Funds Section) in order to exchange experience, set the details of the measure with the aim of smoothly following up on the implemented supports from the Recovery Plan and resilience and the "Program Slovakia 2021-2027". Later in June 2024, a meeting was held again with representatives of the Union of Slovak Cities, where the Environmental Fund provided details about this support aimed to the renovation of existing public buildings from the Modernisation Fund resources. Initiatives received from relevant entities were incorporated into this measure, for example, more green measures, use of RES, reduction in the number of submitted annexes, as well as requests to increase the overall allocation for this support (due to increased demand) and to increase amount of support for individual project/subject. The call proposal will be the subject of comments from relevant stakeholders before its publication. | As specified in Appendix 4, point 1.9 of the document, this measure does not support investments in gaseous fossil fuels. This investment proposal is not financed from either the 1st or the 2nd category of MF funds.
7 | MF 2024-2 SK 0-003 | - | Increasing energy efficiency and reducing greenhouse gas emissions in households of low-income groups | Priority | Large-scale scheme | Not started | not started | not started | not started | 186340000 | 155283333 | 186340000 | 93170000 | 0 | 0 | 0 | n/a | 0 | 7 128 104,4 | 0 | 1224000 | 0 | Real data will only become available during the implementation phase, after the completion of individual projects. | 0 | 152.2386 | Yes: 2023. | The first call is expected to be launched in Q3/2025. | n/a | The launch of the call is expected to take place probably in Q4 2025, after the disbursement of funds from the Recovery and Resilience Plan/REPower EU for this measure, as its financing from the MF resources will continue. | n/a | TBD - the measure has not started | In October 2023 there was held a round table discussion with participation of various stakeholders in order to discuss the investment proposal of a pilot project “Renew the house Mini” and most importantly to define a concept of “energy poverty” in the Slovak conditions, as there is not a strict definition of this term. Among the stakeholders there were representatives of different ministries, regulatory agencies, private sector, and nongovernmental institutions. Taking into account the global energy crisis, participants welcomed the scheme, mainly because it was aimed at low income households. However, there was not a uniform conclusion about the term of “energy poverty”. At the end the definition for the purpose of this scheme was elaborated together with the Statistical office of the Slovak Republic and taking into account the poverty line in Slovakia in the regions supported by the pilot project. | As specified in Appendix 4, point 1.9 of the document, this measure does not support investments in gaseous fossil fuels. This investment proposal is not financed from either the 1st or the 2nd category of MF funds.

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1 | Modernisation of regional distribution system – Phase I priority investment | Ministry of Economy of the Slovak Republic | The whole territory of the Slovak Republic | 126814681 | Modernisation of energy networks, grids for electricity transmission, the increase of interconnections between MS, infrastructure for zero-emission mobility. | prepared for submission in S2/2025 to EIB | 102000000 | Modernisation of energy networks, grids for electricity transmission, the increase of interconnections between MS, infrastructure for zero-emission mobility. Chapters: 2., 3.4., 4.5. | no | Public consultation was held online via MS Teams on 6th of February 2025. More information from the event are available at: https://www.mhsr.sk/energetika/modernizacny-fond/workshop-k-priprave-investicnych-zamerov?csrt=68950614713501582 . | online via MS Teams | public representatives, Ministry of Environment of the Slovak Republic, Ministry of Economy of the Slovak Republic, transmission and distribution system operators | approx. 7 question | Questions regarding the implementation of the investment proposal, including technical details of individual steps and objectives, were answered and explained during the discussion.
2 | Modernisation of transmission system. priority investment | Ministry of Economy of the Slovak Republic | The whole territory of the Slovak Republic | 102895160 | Modernisation of energy networks, grids for electricity transmission, the increase of interconnections between MS, infrastructure for zero-emission mobility. | prepared for submission in S2/2025 to EIB | 98000000 | Modernisation of energy networks, grids for electricity transmission, the increase of interconnections between MS, infrastructure for zero-emission mobility. Chapters: 2., 3.4., 4.5. | no | Public consultation was held online via MS Teams on 6th of February 2025. More information from the event are available at: https://www.mhsr.sk/energetika/modernizacny-fond/workshop-k-priprave-investicnych-zamerov?csrt=68950614713501582 . | online via MS Teams | public representatives, Ministry of Environment of the Slovak Republic, Ministry of Economy of the Slovak Republic, transmission and distribution system operators | approx. 7 question | Questions regarding the implementation of the investment proposal, including technical details of individual steps and objectives, were answered and explained during the discussion.
3 | Investment proposal to support the construction of new renewable energy sources for electricity generation and the modernization of electricity generation in existing renewable energy sources | Ministry of Economy of the Slovak Republic/Ministry of the Environment of the Slovak Republic | The whole territory of the Slovak Republic | 1000000000 | Generation and use of electricity from renewable sources, energy storage | not started | 400000000 | NECP: chapter 2.1.2. Renewable energy | no
4
5
6
7
8
9
10
11
XX

## Beneficiaries
Beneficiaries | Organization identification number | Name of the project | Year | Area | Required resources [€] | Approved resources [€] | Status of application | City | SK region
BES s.r.o. | 35752165 | Modernizácia energetických systémov | 2023 | Energetika | 4461079 | 4461079 | Approved | Bratislava IV | Bratislavský
BYTTERM, a.s. | 31584705 | Horúcovodná prípojka pre VS ZŠ V. Javorku 32 Hliny V, Žilina, Vodovodná prípojka - ZŠ V. Javorku, Žilina, Výmenníková stanica v objekte ZŠ V. Javorku 32, Hliny V, Žilina, Výmena vonkajších sekundárnych rozvodov ÚK a TV v tepelnom okruhu VS VŠDS Hliny, Žilina | 2023 | Energetika | 900276.96 | 900276.96 | Approved | Žilina | Žilinský
COM-therm, spol. s r.o. | 36525782 | Centralizácia vykurovania a zvyšovanie energetickej efektívnosti CZT7/3 - Komárno | 2023 | Energetika | 3655700 | 3655700 | Approved | Bratislava II | Bratislavský
ENGIE Services a.s. | 35966289 | Rekonštrukcia sekundárnych rozvodov ÚK, TÚV a cirkulácie OST 3 Brezová pod Bradlom | 2023 | Energetika | 1099369.89 | 1099369.89 | Approved | Bratislava | Bratislavský
Humenská energetická spoločnosť, s.r.o. | 31728812 | Modernizácia a rekonštrukcia rozvodov tepla v Humennom II. etapa | 2023 | Energetika | 5811771 | 5811771 | Approved | Humenné | Prešovský
KMET Handlová, a.s. | 36334634 | Výstavba, rekonštrukcia a modernizácia výroby tepla a rozvodov tepla v meste Handlová | 2023 | Energetika | 13128774 | 13128774 | Approved | Prievidza | Trenčiansky
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia a modernizácia rozvodov centrálneho zásobovania teplom v meste Martin II. etapa | 2023 | Energetika | 4955425 | 4955425 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Nový zdroj tepla a elektrickej energie - plynové motory a transformátor T10 | 2023 | Energetika | 14725998 | 14725998 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Modernizácia nadzemných častí primárnych napájačov SCZT | 2023 | Energetika | 2375741 | 2375741 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | 2. časť - Modernizácia nadzemných častí primárnych napájačov SCZT | 2023 | Energetika | 6107145.93 | 6107145.93 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia HVTS Ľadoveň III. Etapa, Rekonštrukcia HVTS Ľadoveň IV. Etapa, Rekonštrukcia HVTS Ľadoveň V. etapa, Rekonštrukcia HVTS Ľadoveň prepojenie Juh a Ľadoveň, Rekonštrukcia horúcovodu Martin Podháj III. etapa | 2023 | Energetika | 4707493.6 | 4707493.6 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Zdroj KVET v Teplárni A a Zvýšenie parametrov parných kotlov PK1, PK2 | 2023 | Energetika | 7319853.27 | 7319853.27 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia horúcovodného potrubia vetiev Zvolen-Sekier a Zvolen-Zlatý Potok /časť SO 400 HV rozvod Zvolen -Zlatý Potok/ a Akumulácia tepla | 2023 | Energetika | 11654331.93 | 11654331.93 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Rekonštrukcia horúcovodného potrubia vetiev Zvolen-Sekier a Zvolen-Zlatý Potok - časť SO 500 HV rozvod Zvolen - Podborová | 2023 | Energetika | 969912.38 | 969912.38 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výmena tepelnej izolácie a oplechovania HV potrubí BA východ napájač JUH, Akumulácia tepelnej energie | 2023 | Energetika | 8031006.39 | 8031006.39 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výstavba technológie na vysokoúčinnú kombinovanú výrobu elektriny a tepla ako náhrady za súčasné zdroje v SCZT Západ | 2023 | Energetika | 15000000 | 15000000 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Nová TG1 v závode Martin | 2023 | Energetika | 4107512.82 | 4107512.82 | Approved | Bratislava III | Bratislavský
MH Teplárenský holding, a.s. | 36211541 | Výstavba technológie na vysokoúčinnú kombinovanú výrobu elektriny a tepla ako náhrady za súčasné zdroje v SCZT Západ - Akumulácia | 2023 | Energetika | 1279554.39 | 1279554.39 | Approved | Bratislava III | Bratislavský
Nitrianska teplárenská spoločnosť, a.s. | 36550604 | Rekonštrukcia a modernizácia rozvodov tepla, domové OST v sústave CZT Nitra - Klokočina a Diely | 2023 | Energetika | 3387129 | 3387129 | Approved | Nitra | Nitriansky
Nitrianska teplárenská spoločnosť, a.s. | 36550604 | Vybudovanie rozvodov tepla, chladu a OST pre obytné domy v sústave CZT Nitra - Chrenová | 2023 | Energetika | 1285343 | 1285343 | Approved | Nitra | Nitriansky
SPRAVBYTKOMFORT, a.s. Prešov | 31718523 | Rekonštrukcia sekundárnych rozvodov OST T-1, OST T-2, OST T-3, OST T-4, OST T-6, OST T-7 vrátane vybudovania 124 ks KDOST | 2023 | Energetika | 7528338.43 | 7528338.43 | Approved | Prešov | Prešovský
STEFE Trnava, s. r. o. | 36277215 | Rekonštrukcia vonkajších sekundárnych rozvodov a modernizácia OST na okruhu Družba 1, Trnava | 2023 | Energetika | 2231150.29 | 2231150.29 | Approved | Trnava | Trnavský
STEFE Trnava, s. r. o. | 36277215 | Rekonštrukcia vonkajších sekundárnych rozvodov a modernizácia OST na okruhu Družba 2, Trnava | 2023 | Energetika | 1687162.07 | 1687162.07 | Approved | Trnava | Trnavský
Teplico, s.r.o. | 31621171 | Modernizácia rozvodov tepla CZT Turčianske Teplice II.etapa - Kuzmányho | 2023 | Energetika | 1559357.02 | 1559357.02 | Approved | Turčianske Teplice | Žilinský
Teplo GGE s. r. o. | 36012424 | Rekonštrukcia a modernizácia rozvodov CZT okruh OST EG 1, 2 Rozkvet, Považská Bystrica | 2023 | Energetika | 2073495.36 | 2073495.36 | Approved | Považská Bystrica | Trenčiansky
Teplárne ZM s.r.o. | 35785225 | Modernizácia energetických systémov | 2023 | Energetika | 2570331 | 2570331 | Approved | Zlaté Moravce | Nitriansky
TERMMING, a.s. | 35972254 | Rekonštrukcia primárneho rozvodu UK medzi šachtou na Brnianskej ul. a OST2 v Malackách | 2023 | Energetika | 584043 | 584043 | Approved | Bratislava III | Bratislavský
TOMA, s.r.o. | 31421695 | Rozšírenie teplovodnej siete TOMA, s.r.o. v meste Topoľčany (tepelné prípojky a OST) | 2023 | Energetika | 702606 | 702606 | Approved | Topoľčany | Nitriansky
Veolia Energia Levice, a.s. | 35968486 | Rekonštrukcia rozvodov okruhu OS86 Levice | 2023 | Energetika | 1553692 | 1553692 | Approved | Bratislava V | Bratislavský
Veolia Energia Levice, a.s. | 35968486 | Rekonštrukcia okruhu OS 46, Rekonštrukcia HVN CZT – Rybníky 5, Levice | 2023 | Energetika | 4352230.92 | 4352230.92 | Approved | Bratislava V | Bratislavský
Veolia Energia Vráble, a.s. | 35802871 | Rekonštrukcia rozvodov ÚK a TÚV sídliska Lúky – Malá strana, Vráble; Realizácia Smart metering sídliska Lúky – Malá strana, Vráble | 2023 | Energetika | 610371.32 | 610371.32 | Approved | Nitra | Nitriansky
Veolia Utilities Žiar nad Hronom, a.s. | 44069472 | Rekonštrukcia výmenníkovej stanice a rozvodov tepla | 2023 | Energetika | 3964111 | 3964111 | Approved | Žiar nad Hronom | Banskobystrický
Veolia Utilities Žiar nad Hronom, a.s. | 44069472 | Modernizácia zdroja VÚ KVET vo Veolia Utilities Žiar nad Hronom, a.s.; Výroba a distribúcia ľadovej vody vo Veolia Utilities Žiar nad Hronom, a.s. | 2023 | Energetika | 5783291.12 | 5783291.12 | Approved | Žiar nad Hronom | Banskobystrický

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia